## INSTRUCTION
Component | Location | Description & Business Insight | Dashboard Component | Location | Analytical & Operational Purpose
**Interactive Filter Bar** | `B4:G5` | Select specific **Floors** (`1st Floor` to `4th Floor`), **Room Types** (`King room`, `Twin room`, `Suite room`), or individual **Room Numbers** (`101` to `418`) to immediately refocus dashboard analytics. | **Interactive Filters** | `B4:H5` | Dynamic dropdowns to filter calculations by **Floor** (`All Floors`, `Ground Floor`, `Terrace`), **Area Type** (`All Areas`, `Parent Areas`, `Sub-Areas`), and select individual spaces for inspection.
**Overall Progress Card** | `B7:E10` | Displays total project completion percentage (`55.4%`), counting completed milestones out of valid items while strictly excluding `NOT VALID` (N/A) scope. | **Executive KPI Cards** | `B7:U10` | 5 high-impact cards tracking **Overall Completion %** (`13.8%`), **Areas 100% Complete** (`0 / 59`), **Primary Bottleneck Trade** (`Furniture Work` at `1.0%`), **Active Ongoing Tasks** (`54`), and **Total Not Started Tasks** (`2,053`).
**Room Turn-Over KPI** | `F7:I10` | Shows fully finished rooms (`0 / 100`) versus rooms with active or pending items (`100 Rooms Pending`). | **Trade Completion Chart** | `B12:I24` | Horizontal bar chart visualizing all 9 trade categories ranked dynamically from worst to best completion percentage.
**Primary Bottleneck Alert** | `J7:M10` | Highlights the lowest-performing trade milestone—**Furnishing Work** (`2.0%` complete)—to surface critical path delays before handover. | **Floor Status Breakdown** | `J12:Q24` | Stacked column chart comparing completed, ongoing, and not started checklist items between Ground Floor and Terrace.
**Active WIP & Mobilization** | `N7:U10` | Quantifies total tasks currently **Ongoing** (`474` active tasks in progress) and total **Not Started** (`2,434` items awaiting preceding trades). | **Floor Completion % Chart** | `R12:U24` | Column chart benchmarking overall completion rates between Ground Floor (`15.0%`) and Terrace (`0.5%`).
**Trade Bottleneck Chart** | `B12:I24` | Horizontal bar chart displaying all 12 trade categories sorted in ascending order from lowest completion to highest completion (Furnishing Work → Waterproofing). | **Single Area Inspection Panel** | `V7:Z35` | Dedicated inspection cockpit displaying space metadata, 9-trade checklist breakdown, status badges, checklist counts, and punch lists for ongoing and lagging tasks.
**Floor Status Breakdown** | `K12:P24` | Stacked column chart visualizing Completed (green), Ongoing (amber), and Not Started (grey) task distribution across all 4 hotel floors. | **Master Progress Heat Matrix** | `B27:Q87` | Comprehensive live register of all 59 public areas detailing trade progress percentages, overall completion rates, area status, and handover readiness.
**Room Type Completion** | `R12:U24` | Column chart comparing progress across room configurations (King room: `55.5%`, Twin room: `57.9%`, Suite room: `45.3%`).
**Room Inspection Panel** | `V8:Z33` | Dedicated side panel showing room floor, room type, completion rate, status of each of the 12 trades, item checklist totals, and an exact list of **current ongoing tasks** inside the inspected room.
**Trade Progress Heat Matrix** | `B36:Q65+` | Compact room-by-trade matrix color-coded by completion: **Green** = Completed (`100%`), **Amber** = Ongoing/Partial (`1%–99%`), and **Slate Grey** = Not Started (`0%`).

## Dashboard
HOTEL PROJECT — OVERALL COMPLETION DASHBOARD
Rolls up automatically from Rooms Tracker, Public Areas Tracker and Landscaping Tracker. Nothing on this sheet should be typed over.
Section | Items Tracked | Avg. Completion % | Weight in Overall %
Rooms (100 Keys) | 100 | 47.14% | 54.64%
Public Areas | 59 | 17.55% | 32.24%
PASSAGE | 24 | 27.23% | 13.11%
OVERALL PROJECT COMPLETION |  | 34.99%
Trade-wise Average Completion (Rooms Tracker)
Trade | Avg. % Across 100 Rooms
Civil Work | 72.56%
Waterproofing | 100%
Electrical | 50%
ELV | 1%
Plumbing | 62.78%
Paint | 53.86%
Fire | 69%
HVAC | 62.56%
Tiles | 83.71%
False Ceiling | 40%
Furniture Work | 25.18%
Furnishing Work | 1.667%
Rooms by Status
Status | No. of Rooms
Completed | 0
In Progress | 92
Not Started | 6

## 100_ROOMS-DASHBOARD
[22 empty] | Trade Category | Start Col | End Col | Completed | Ongoing | Not Started | Total Valid | Completion % |  | Trade Category | Completion % |  | Floor | Completed | Ongoing | Not Started |  | Room Type | Completed | Ongoing | Not Started | Total Valid | Completion % | Filtered Rooms
HOTEL CONSTRUCTION EXECUTIVE DASHBOARD | [21 empty] | Civil Work | E | I | 230 | 87 | 0 | 317 | 0.72555 |  | Fixtures and OS&E | 0.005 |  | 1st Floor | 1082 | 100 | 900 |  | King room | 2511 | 307 | 2519 | 5337 | 0.47049 | 101
Real-time Milestones, Trade Completion Analytics & Room Inspection Status ¦ Data Source: 100 ROOMS | [21 empty] | Waterproofing | J | L | 300 | 0 | 0 | 300 | 1 |  | ELV | 0.01 |  | 2nd Floor | 1280 | 144 | 1172 |  | Twin room | 1316 | 144 | 1218 | 2678 | 0.49141 | 102
FLOOR FILTER |  | ROOM TYPE FILTER |  | ROOM INSPECTION | [17 empty] | Electrical | M | X | 600 | 46 | 554 | 1200 | 0.5 |  | Furnishing Work | 0.016667 |  | 3rd Floor | 1092 | 141 | 1163 |  | Suite room | 234 | 25 | 343 | 602 | 0.3887 | 103
All Floors |  | All Types |  | 101 | [17 empty] | ELV | Y | Z | 2 | 1 | 197 | 200 | 0.01 |  | Furniture Work | 0.25182 |  | 4th Floor | 607 | 91 | 845 | [7 empty] | 104
[22 empty] | Plumbing | AA | AI | 501 | 1 | 296 | 798 | 0.62782 |  | False Ceiling | 0.4 | [12 empty] | 105
OVERALL COMPLETION |  |  |  | ROOMS 100% COMPLETE |  |  |  | PRIMARY BOTTLENECK |  |  |  | ACTIVE ONGOING (WIP) |  |  |  | TOTAL NOT STARTED | [5 empty] | Paint | AJ | AP | 377 | 7 | 316 | 700 | 0.53857 |  | Electrical | 0.5 | [12 empty] | 106
47.14% |  |  |  | 0 / 100 |  |  |  | Fixtures and OS&E |  |  |  | 476 |  |  |  | 4078 |  | ROOM INSPECTION PANEL — ROOM 101 |  |  |  | Fire | AQ | AT | 276 | 0 | 124 | 400 | 0.69 |  | Paint | 0.53857 | [12 empty] | 107
Completed: 4,061 items |  |  |  | Pending: 100 Rooms |  |  |  | Completion: 0.5% |  |  |  | Active Tasks across Rooms |  |  |  | Tasks Pending Mobilization |  | Floor: | 1st Floor | Type: | King room | HVAC | AU | BC | 563 | 0 | 337 | 900 | 0.62556 |  | HVAC | 0.62556 | [12 empty] | 108
(Excludes NOT VALID items) |  |  |  | Lowest Milestone Trade |  |  |  | Requires Supervision |  |  |  | Awaiting Preceding Trades | [5 empty] | Overall: | 54.02% | Status: | ON GOING | Tiles | BD | BJ | 586 | 3 | 111 | 700 | 0.83714 |  | Plumbing | 0.62782 | [12 empty] | 109
[18 empty] | TRADE BREAKDOWN |  |  |  | False Ceiling | BK | BM | 120 | 169 | 11 | 300 | 0.4 |  | Fire | 0.69 | [12 empty] | 110
[18 empty] | Civil Work |  | 100% | COMPLETED | Furniture Work | BN | BX | 277 | 149 | 674 | 1100 | 0.25182 |  | Glass Work | 0.71667 | [12 empty] | 111
[18 empty] | Waterproofing |  | 100% | COMPLETED | Furnishing Work | BY | CD | 10 | 0 | 590 | 600 | 0.016667 |  | Civil Work | 0.72555 | [12 empty] | 112
[18 empty] | Electrical |  | 50% | ON GOING | Glass Work | CE | CG | 215 | 13 | 72 | 300 | 0.71667 |  | Tiles | 0.83714 | [12 empty] | 113
[18 empty] | ELV |  | 0% | NOT STARTED | Fixtures and OS&E | CH | CO | 4 | 0 | 796 | 800 | 0.005 |  | Waterproofing | 1 | [12 empty] | 114
[18 empty] | Plumbing |  | 62.5% | ON GOING | Overall Completion % | 0.47139 | [21 empty] | 115
[18 empty] | Paint |  | 57.14% | ON GOING | Total Completed | 4061 | [21 empty] | 116
[18 empty] | Fire |  | 75% | ON GOING | Total Ongoing | 476 | [21 empty] | 117
[18 empty] | HVAC |  | 66.67% | ON GOING | Total Not Started | 4078 | [21 empty] | 118
[18 empty] | Tiles |  | 85.71% | ON GOING | Bottleneck Category | Fixtures and OS&E | [21 empty] | 119
[18 empty] | False Ceiling |  | 66.67% | ON GOING | Bottleneck Rate | 0.005 | [21 empty] | 120
[18 empty] | Furniture Work |  | 45.45% | ON GOING | Rooms 100% Complete | 0 | [21 empty] | 121
[18 empty] | Furnishing Work |  | 0% | NOT STARTED | Rooms Pending | 100 | [21 empty] | 122
[18 empty] | Glass Work |  | 100% | COMPLETED | Room No | Floor | Type | Civil | Waterproofing | Electrical | ELV | Plumbing | Paint | Fire | HVAC | Tiles | Ceiling | Furniture | Furnishing | Glass | Fixtures and OS&E | Overall % | Is Complete | Include In Filter |  |  |  | 123
[18 empty] | Fixtures and OS&E |  | 0% | NOT STARTED | 101 | 1st Floor | King room | 1 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.45455 | 0 | 1 | 0 | 0.54023 | 0 | 1 |  |  |  | 124
[18 empty] | CHECKLIST ITEM SUMMARY |  |  |  | 102 | 1st Floor | King room | 1 | 1 | 0.83333 | 0.5 | 0.75 | 0.85714 | 1 | 0.66667 | 1 | 1 | 1 | 0.83333 | 1 | 0.25 | 0.81609 | 0 | 1 |  |  |  | 201
ROOM × TRADE PROGRESS HEAT MATRIX ¦ LIVE WORK-IN-PROGRESS & BOTTLENECK TRACKER | [17 empty] | Completed Items |  |  | 47 | 103 | 1st Floor | Twin room | 1 | 1 | 0.83333 | 0.5 | 0.75 | 0.85714 | 1 | 0.66667 | 1 | 1 | 1 | 0.83333 | 1 | 0.25 | 0.81609 | 0 | 1 |  |  |  | 202
Room | Floor | Type | Civil | Waterpr. | Electrical | ELV | Plumbing | Paint | Fire | HVAC | Tiles | Ceiling | Furniture | Furnishing | Glass | OS&E | Overall % | Ongoing (WIP) Items |  |  | 9 | 104 | 1st Floor | Twin room | 1 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.45455 | 0 | 1 | 0 | 0.54023 | 0 | 1 |  |  |  | 203
101 | 1st Floor | King room | 100% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 45.45% | 0% | 100% | 0% | 54.02% | Not Started Items |  |  | 31 | 105 | 1st Floor | King room | 1 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.36364 | 0 | 1 | 0 | 0.52874 | 0 | 1 |  |  |  | 204
102 | 1st Floor | King room | 100% | 100% | 83.33% | 50% | 75% | 85.71% | 100% | 66.67% | 100% | 100% | 100% | 83.33% | 100% | 25% | 81.61% | Not Valid (N/A) Items |  |  | 1 | 106 | 1st Floor | King room | 1 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.36364 | 0 | 1 | 0 | 0.52874 | 0 | 1 |  |  |  | 205
103 | 1st Floor | Twin room | 100% | 100% | 83.33% | 50% | 75% | 85.71% | 100% | 66.67% | 100% | 100% | 100% | 83.33% | 100% | 25% | 81.61% | CURRENT ONGOING TASKS IN ROOM |  |  |  | 107 | 1st Floor | Twin room | 1 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.36364 | 0 | 1 | 0 | 0.52874 | 0 | 1 |  |  |  | 206
104 | 1st Floor | Twin room | 100% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 45.45% | 0% | 100% | 0% | 54.02% | light Fitting , Exposed / sanitary fixture, final touchup, Trap Door, Wardrobe+LUGGUAGE, Mini Bar, Bed Back Panelling, TV Unit, Loose Furniture |  |  |  | 108 | 1st Floor | Twin room | 1 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.27273 | 0 | 1 | 0 | 0.51724 | 0 | 1 |  |  |  | 207
105 | 1st Floor | King room | 100% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 36.36% | 0% | 100% | 0% | 52.87% |  |  |  |  | 109 | 1st Floor | King room | 1 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.36364 | 0 | 1 | 0 | 0.52874 | 0 | 1 |  |  |  | 208
106 | 1st Floor | King room | 100% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 36.36% | 0% | 100% | 0% | 52.87% | NOT STARTED TASKS IN ROOM |  |  |  | 110 | 1st Floor | Twin room | 1 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.36364 | 0 | 1 | 0 | 0.52874 | 0 | 1 |  |  |  | 209
107 | 1st Floor | Twin room | 100% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 36.36% | 0% | 100% | 0% | 52.87% | Fire Alarm / Sounder cabling, Telephone / EPABX cabling, Switches work, MCCB / RCCB installation, ROOM ELECTRICAL TESTING, Electronic Door Locks, ELV Funcitonal Testing, Final trap & Drain Connection, Final water flow / leakage Check, 1ST coat paint, 2ND coat paint, final touchup, Smoke Detecters, VRV outdoors, Diffuser / Grille, HVAC Commissioning, WALL EPOXY, Rugs, Carpet, SPC Flooring, Curtain, Bed Back Cushioning, Art work / painting, TV installation, Minibar fridge, Safe, kettle / Tea tray, Telephone, Bathroom accessories / hair dryer, Decorative lamps, Room accessories / signage |  |  |  | 111 | 1st Floor | King room | 1 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.36364 | 0 | 1 | 0 | 0.53409 | 0 | 1 |  |  |  | 210
108 | 1st Floor | Twin room | 100% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 27.27% | 0% | 100% | 0% | 51.72% |  |  |  |  | 112 | 1st Floor | Twin room | 1 | 1 | 0.5 | 0 | 0.625 | 0.42857 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.27273 | 0 | 1 | 0 | 0.5 | 0 | 1 |  |  |  | 211
109 | 1st Floor | King room | 100% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 36.36% | 0% | 100% | 0% | 52.87% |  |  |  |  | 113 | 1st Floor | King room | 1 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.36364 | 0 | 1 | 0 | 0.52326 | 0 | 1 |  |  |  | 212
110 | 1st Floor | Twin room | 100% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 36.36% | 0% | 100% | 0% | 52.87% |  |  |  |  | 114 | 1st Floor | King room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.27273 | 0 | 1 | 0 | 0.5 | 0 | 1 |  |  |  | 213
111 | 1st Floor | King room | 100% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 36.36% | 0% | 100% | 0% | 53.41% |  |  |  |  | 115 | 1st Floor | Twin room | 0.75 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.27273 | 0 | 0.33333 | 0 | 0.48276 | 0 | 1 |  |  |  | 214
112 | 1st Floor | Twin room | 100% | 100% | 50% | 0% | 62.5% | 42.86% | 75% | 66.67% | 85.71% | 66.67% | 27.27% | 0% | 100% | 0% | 50% |  |  |  |  | 116 | 1st Floor | King room | 0.75 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.27273 | 0 | 0.33333 | 0 | 0.48276 | 0 | 1 |  |  |  | 215
113 | 1st Floor | King room | 100% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 36.36% | 0% | 100% | 0% | 52.33% |  |  |  |  | 117 | 1st Floor | Twin room | 0.75 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.27273 | 0 | 0.33333 | 0 | 0.48276 | 0 | 1 |  |  |  | 216
114 | 1st Floor | King room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 27.27% | 0% | 100% | 0% | 50% |  |  |  |  | 118 | 1st Floor | Suite room | 0.75 | 1 | 0.083333 | 0 | 0.625 | 0.14286 | 0.75 | 0.44444 | 0.85714 | 0 | 0 | 0 | 1 | 0 | 0.33333 | 0 | 1 |  |  |  | 217
115 | 1st Floor | Twin room | 75% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 27.27% | 0% | 33.33% | 0% | 48.28% |  |  |  |  | 119 | 1st Floor | Twin room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.27273 | 0 | 1 | 0 | 0.5 | 0 | 1 |  |  |  | 218
116 | 1st Floor | King room | 75% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 27.27% | 0% | 33.33% | 0% | 48.28% |  |  |  |  | 120 | 1st Floor | King room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.27273 | 0 | 1 | 0 | 0.5 | 0 | 1 |  |  |  | 219
117 | 1st Floor | Twin room | 75% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 27.27% | 0% | 33.33% | 0% | 48.28% |  |  |  |  | 121 | 1st Floor | Suite room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.18182 | 0 | 0.33333 | 0 | 0.46512 | 0 | 1 |  |  |  | 220
118 | 1st Floor | Suite room | 75% | 100% | 8.333% | 0% | 62.5% | 14.29% | 75% | 44.44% | 85.71% | 0% | 0% | 0% | 100% | 0% | 33.33% |  |  |  |  | 122 | 1st Floor | Suite room | 0.75 | 1 | 0.25 | 0 | 0.5 | 0.14286 | 0.75 | 0.66667 | 0.28571 | 0 | 0 | 0 | 0 | 0 | 0.28736 | 0 | 1 |  |  |  | 221
119 | 1st Floor | Twin room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 27.27% | 0% | 100% | 0% | 50% |  |  |  |  | 123 | 1st Floor | King room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.36364 | 0 | 0.66667 | 0 | 0.5 | 0 | 1 |  |  |  | 222
120 | 1st Floor | King room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 27.27% | 0% | 100% | 0% | 50% |  |  |  |  | 124 | 1st Floor | King room | 0.75 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.36364 | 0 | 0.66667 | 0 | 0.50575 | 0 | 1 |  |  |  | 223
121 | 1st Floor | Suite room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 18.18% | 0% | 33.33% | 0% | 46.51% |  |  |  |  | 201 | 2nd Floor | King room | 0.75 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.36364 | 0 | 1 | 0 | 0.51724 | 0 | 1 |  |  |  | 224
122 | 1st Floor | Suite room | 75% | 100% | 25% | 0% | 50% | 14.29% | 75% | 66.67% | 28.57% | 0% | 0% | 0% | 0% | 0% | 28.74% |  |  |  |  | 202 | 2nd Floor | King room | 0.75 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.36364 | 0 | 1 | 0 | 0.51724 | 0 | 1 |  |  |  | 225
123 | 1st Floor | King room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 36.36% | 0% | 66.67% | 0% | 50% |  |  |  |  | 203 | 2nd Floor | Twin room | 0.75 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.36364 | 0 | 1 | 0 | 0.51724 | 0 | 1 |  |  |  | 226
124 | 1st Floor | King room | 75% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 36.36% | 0% | 66.67% | 0% | 50.57% |  |  |  |  | 204 | 2nd Floor | Twin room | 0.75 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.36364 | 0 | 1 | 0 | 0.51724 | 0 | 1 |  |  |  | 227
201 | 2nd Floor | King room | 75% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 36.36% | 0% | 100% | 0% | 51.72% |  |  |  |  | 205 | 2nd Floor | King room | 0.75 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.36364 | 0 | 1 | 0 | 0.51724 | 0 | 1 |  |  |  | 228
202 | 2nd Floor | King room | 75% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 36.36% | 0% | 100% | 0% | 51.72% |  |  |  |  | 206 | 2nd Floor | King room | 0.75 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.27273 | 0 | 1 | 0 | 0.50575 | 0 | 1 |  |  |  | 229
203 | 2nd Floor | Twin room | 75% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 36.36% | 0% | 100% | 0% | 51.72% |  |  |  |  | 207 | 2nd Floor | Twin room | 0.75 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.36364 | 0 | 1 | 0 | 0.51724 | 0 | 1 |  |  |  | 230
204 | 2nd Floor | Twin room | 75% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 36.36% | 0% | 100% | 0% | 51.72% |  |  |  |  | 208 | 2nd Floor | Twin room | 0.75 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.36364 | 0 | 1 | 0 | 0.51724 | 0 | 1 |  |  |  | 301
205 | 2nd Floor | King room | 75% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 36.36% | 0% | 100% | 0% | 51.72% |  |  |  |  | 209 | 2nd Floor | King room | 0.75 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.36364 | 0 | 1 | 0 | 0.51724 | 0 | 1 |  |  |  | 302
206 | 2nd Floor | King room | 75% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 27.27% | 0% | 100% | 0% | 50.57% |  |  |  |  | 210 | 2nd Floor | Twin room | 0.75 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.36364 | 0 | 1 | 0 | 0.51724 | 0 | 1 |  |  |  | 303
207 | 2nd Floor | Twin room | 75% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 36.36% | 0% | 100% | 0% | 51.72% |  |  |  |  | 211 | 2nd Floor | King room | 0.8 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.27273 | 0 | 1 | 0 | 0.51136 | 0 | 1 |  |  |  | 304
208 | 2nd Floor | Twin room | 75% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 36.36% | 0% | 100% | 0% | 51.72% |  |  |  |  | 212 | 2nd Floor | Twin room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.14286 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.18182 | 0 | 0.33333 | 0 | 0.43023 | 0 | 1 |  |  |  | 305
209 | 2nd Floor | King room | 75% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 36.36% | 0% | 100% | 0% | 51.72% |  |  |  |  | 213 | 2nd Floor | King room | 0.5 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.36364 | 0 | 1 | 0 | 0.50588 | 0 | 1 |  |  |  | 306
210 | 2nd Floor | Twin room | 75% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 36.36% | 0% | 100% | 0% | 51.72% |  |  |  |  | 214 | 2nd Floor | King room | 0.5 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.36364 | 0 | 0.66667 | 0 | 0.49412 | 0 | 1 |  |  |  | 307
211 | 2nd Floor | King room | 80% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 27.27% | 0% | 100% | 0% | 51.14% |  |  |  |  | 215 | 2nd Floor | Twin room | 0.75 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.27273 | 0 | 0.66667 | 0 | 0.49425 | 0 | 1 |  |  |  | 308
212 | 2nd Floor | Twin room | 66.67% | 100% | 50% | 0% | 62.5% | 14.29% | 75% | 66.67% | 85.71% | 66.67% | 18.18% | 0% | 33.33% | 0% | 43.02% |  |  |  |  | 216 | 2nd Floor | King room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.18182 | 0 | 1 | 0 | 0.48837 | 0 | 1 |  |  |  | 309
213 | 2nd Floor | King room | 50% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 36.36% | 0% | 100% | 0% | 50.59% |  |  |  |  | 217 | 2nd Floor | Twin room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.36364 | 0 | 1 | 0 | 0.51163 | 0 | 1 |  |  |  | 310
214 | 2nd Floor | King room | 50% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 36.36% | 0% | 66.67% | 0% | 49.41% |  |  |  |  | 218 | 2nd Floor | King room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.18182 | 0 | 0.33333 | 0 | 0.46512 | 0 | 1 |  |  |  | 311
215 | 2nd Floor | Twin room | 75% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 27.27% | 0% | 66.67% | 0% | 49.43% |  |  |  |  | 219 | 2nd Floor | King room | 0.75 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.27273 | 0 | 0.33333 | 0 | 0.48276 | 0 | 1 |  |  |  | 312
216 | 2nd Floor | King room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 18.18% | 0% | 100% | 0% | 48.84% |  |  |  |  | 220 | 2nd Floor | King room | 0.75 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.33333 | 0.18182 | 0 | 0.33333 | 0 | 0.45977 | 0 | 1 |  |  |  | 313
217 | 2nd Floor | Twin room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 36.36% | 0% | 100% | 0% | 51.16% |  |  |  |  | 221 | 2nd Floor | King room | 0.75 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.33333 | 0.36364 | 0 | 1 | 0 | 0.50575 | 0 | 1 |  |  |  | 314
218 | 2nd Floor | King room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 18.18% | 0% | 33.33% | 0% | 46.51% |  |  |  |  | 222 | 2nd Floor | Twin room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.33333 | 0.36364 | 0 | 1 | 0 | 0.5 | 0 | 1 |  |  |  | 315
219 | 2nd Floor | King room | 75% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 27.27% | 0% | 33.33% | 0% | 48.28% |  |  |  |  | 223 | 2nd Floor | King room | 0.75 | 1 | 0.5 | 0 | 0.625 | 0.28571 | 0.75 | 0.66667 | 0.85714 | 0.33333 | 0.090909 | 0 | 1 | 0 | 0.44828 | 0 | 1 |  |  |  | 316
220 | 2nd Floor | King room | 75% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 33.33% | 18.18% | 0% | 33.33% | 0% | 45.98% |  |  |  |  | 224 | 2nd Floor | Suite room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.28571 | 0.75 | 0.66667 | 0.85714 | 0.33333 | 0.090909 | 0 | 0.66667 | 0 | 0.43023 | 0 | 1 |  |  |  | 317
221 | 2nd Floor | King room | 75% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 33.33% | 36.36% | 0% | 100% | 0% | 50.57% |  |  |  |  | 225 | 2nd Floor | Suite room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.33333 | 0.090909 | 0 | 0.66667 | 0 | 0.45349 | 0 | 1 |  |  |  | 318
222 | 2nd Floor | Twin room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 33.33% | 36.36% | 0% | 100% | 0% | 50% |  |  |  |  | 226 | 2nd Floor | King room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.18182 | 0 | 0.33333 | 0 | 0.46512 | 0 | 1 |  |  |  | 319
223 | 2nd Floor | King room | 75% | 100% | 50% | 0% | 62.5% | 28.57% | 75% | 66.67% | 85.71% | 33.33% | 9.091% | 0% | 100% | 0% | 44.83% |  |  |  |  | 227 | 2nd Floor | King room | 0.75 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.27273 | 0 | 1 | 0 | 0.50575 | 0 | 1 |  |  |  | 320
224 | 2nd Floor | Suite room | 66.67% | 100% | 50% | 0% | 62.5% | 28.57% | 75% | 66.67% | 85.71% | 33.33% | 9.091% | 0% | 66.67% | 0% | 43.02% |  |  |  |  | 228 | 2nd Floor | King room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.27273 | 0 | 0.66667 | 0 | 0.48837 | 0 | 1 |  |  |  | 321
225 | 2nd Floor | Suite room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 33.33% | 9.091% | 0% | 66.67% | 0% | 45.35% |  |  |  |  | 229 | 2nd Floor | King room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.27273 | 0 | 1 | 0 | 0.5 | 0 | 1 |  |  |  | 322
226 | 2nd Floor | King room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 18.18% | 0% | 33.33% | 0% | 46.51% |  |  |  |  | 230 | 2nd Floor | King room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.27273 | 0 | 0.66667 | 0 | 0.48837 | 0 | 1 |  |  |  | 323
227 | 2nd Floor | King room | 75% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 27.27% | 0% | 100% | 0% | 50.57% |  |  |  |  | 301 | 3rd Floor | King room | 0.5 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.18182 | 0 | 1 | 0 | 0.48235 | 0 | 1 |  |  |  | 324
228 | 2nd Floor | King room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 27.27% | 0% | 66.67% | 0% | 48.84% |  |  |  |  | 302 | 3rd Floor | King room | 0.5 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.18182 | 0 | 0.66667 | 0 | 0.47059 | 0 | 1 |  |  |  | 325
229 | 2nd Floor | King room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 27.27% | 0% | 100% | 0% | 50% |  |  |  |  | 303 | 3rd Floor | Twin room | 0.5 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.18182 | 0 | 1 | 0 | 0.48235 | 0 | 1 |  |  |  | 326
230 | 2nd Floor | King room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 27.27% | 0% | 66.67% | 0% | 48.84% |  |  |  |  | 304 | 3rd Floor | Twin room | 0.5 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.66667 | 0.18182 | 0 | 1 | 0 | 0.48235 | 0 | 1 |  |  |  | 327
301 | 3rd Floor | King room | 50% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 18.18% | 0% | 100% | 0% | 48.24% |  |  |  |  | 305 | 3rd Floor | King room | 0.5 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.33333 | 0.18182 | 0 | 1 | 0 | 0.47059 | 0 | 1 |  |  |  | 328
302 | 3rd Floor | King room | 50% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 18.18% | 0% | 66.67% | 0% | 47.06% |  |  |  |  | 306 | 3rd Floor | King room | 0.5 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.33333 | 0.18182 | 0 | 1 | 0 | 0.47059 | 0 | 1 |  |  |  | 401
303 | 3rd Floor | Twin room | 50% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 18.18% | 0% | 100% | 0% | 48.24% |  |  |  |  | 307 | 3rd Floor | Twin room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.33333 | 0.18182 | 0 | 1 | 0 | 0.47674 | 0 | 1 |  |  |  | 402
304 | 3rd Floor | Twin room | 50% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 66.67% | 18.18% | 0% | 100% | 0% | 48.24% |  |  |  |  | 308 | 3rd Floor | Twin room | 0.5 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.33333 | 0.18182 | 0 | 1 | 0 | 0.47059 | 0 | 1 |  |  |  | 403
305 | 3rd Floor | King room | 50% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 33.33% | 18.18% | 0% | 100% | 0% | 47.06% |  |  |  |  | 309 | 3rd Floor | King room | 0.5 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0 | 0.18182 | 0 | 1 | 0 | 0.45882 | 0 | 1 |  |  |  | 404
306 | 3rd Floor | King room | 50% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 33.33% | 18.18% | 0% | 100% | 0% | 47.06% |  |  |  |  | 310 | 3rd Floor | Twin room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.33333 | 0.18182 | 0 | 1 | 0 | 0.47674 | 0 | 1 |  |  |  | 405
307 | 3rd Floor | Twin room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 33.33% | 18.18% | 0% | 100% | 0% | 47.67% |  |  |  |  | 311 | 3rd Floor | King room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.33333 | 0.18182 | 0 | 0.66667 | 0 | 0.46512 | 0 | 1 |  |  |  | 406
308 | 3rd Floor | Twin room | 50% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 33.33% | 18.18% | 0% | 100% | 0% | 47.06% |  |  |  |  | 312 | 3rd Floor | Twin room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.28571 | 0.75 | 0.66667 | 0.85714 | 0.33333 | 0.18182 | 0 | 0 | 0 | 0.4186 | 0 | 1 |  |  |  | 407
309 | 3rd Floor | King room | 50% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 0% | 18.18% | 0% | 100% | 0% | 45.88% |  |  |  |  | 313 | 3rd Floor | King room | 0.5 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0 | 0.18182 | 0 | 0.66667 | 0 | 0.44706 | 0 | 1 |  |  |  | 408
310 | 3rd Floor | Twin room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 33.33% | 18.18% | 0% | 100% | 0% | 47.67% |  |  |  |  | 314 | 3rd Floor | King room | 0.5 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0 | 0.18182 | 0 | 0.66667 | 0 | 0.44706 | 0 | 1 |  |  |  | 409
311 | 3rd Floor | King room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 33.33% | 18.18% | 0% | 66.67% | 0% | 46.51% |  |  |  |  | 315 | 3rd Floor | Twin room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0 | 0.18182 | 0 | 0.66667 | 0 | 0.45349 | 0 | 1 |  |  |  | 410
312 | 3rd Floor | Twin room | 66.67% | 100% | 50% | 0% | 62.5% | 28.57% | 75% | 66.67% | 85.71% | 33.33% | 18.18% | 0% | 0% | 0% | 41.86% |  |  |  |  | 316 | 3rd Floor | King room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0 | 0.18182 | 0 | 0.66667 | 0 | 0.45349 | 0 | 1 |  |  |  | 411
313 | 3rd Floor | King room | 50% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 0% | 18.18% | 0% | 66.67% | 0% | 44.71% |  |  |  |  | 317 | 3rd Floor | Twin room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0 | 0.18182 | 0 | 0.66667 | 0 | 0.45349 | 0 | 1 |  |  |  | 412
314 | 3rd Floor | King room | 50% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 0% | 18.18% | 0% | 66.67% | 0% | 44.71% |  |  |  |  | 318 | 3rd Floor | King room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0 | 0.18182 | 0 | 0.33333 | 0 | 0.44186 | 0 | 1 |  |  |  | 413
315 | 3rd Floor | Twin room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 0% | 18.18% | 0% | 66.67% | 0% | 45.35% |  |  |  |  | 319 | 3rd Floor | King room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0 | 0.18182 | 0 | 0.33333 | 0 | 0.44186 | 0 | 1 |  |  |  | 414
316 | 3rd Floor | King room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 0% | 18.18% | 0% | 66.67% | 0% | 45.35% |  |  |  |  | 320 | 3rd Floor | Twin room | 0.75 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0 | 0.18182 | 0 | 0.66667 | 0 | 0.45977 | 0 | 1 |  |  |  | 415
317 | 3rd Floor | Twin room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 0% | 18.18% | 0% | 66.67% | 0% | 45.35% |  |  |  |  | 321 | 3rd Floor | King room | 0.75 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0 | 0.18182 | 0 | 0.66667 | 0 | 0.45977 | 0 | 1 |  |  |  | 416
318 | 3rd Floor | King room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 0% | 18.18% | 0% | 33.33% | 0% | 44.19% |  |  |  |  | 322 | 3rd Floor | King room | 0.75 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0 | 0.18182 | 0 | 0.33333 | 0 | 0.44828 | 0 | 1 |  |  |  | 417
319 | 3rd Floor | King room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 0% | 18.18% | 0% | 33.33% | 0% | 44.19% |  |  |  |  | 323 | 3rd Floor | Suite room | 0.5 | 1 | 0.5 | 0 | 0.625 | 0.28571 | 0.75 | 0.66667 | 0.85714 | 0 | 0.18182 | 0 | 0.66667 | 0 | 0.42353 | 0 | 1 |  |  |  | 418
320 | 3rd Floor | Twin room | 75% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 0% | 18.18% | 0% | 66.67% | 0% | 45.98% |  |  |  |  | 324 | 3rd Floor | King room | 0.5 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0 | 0.18182 | 0 | 0.33333 | 0 | 0.43529 | 0 | 1
321 | 3rd Floor | King room | 75% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 0% | 18.18% | 0% | 66.67% | 0% | 45.98% |  |  |  |  | 325 | 3rd Floor | King room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0 | 0.18182 | 0 | 0.33333 | 0 | 0.44186 | 0 | 1
322 | 3rd Floor | King room | 75% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 0% | 18.18% | 0% | 33.33% | 0% | 44.83% |  |  |  |  | 326 | 3rd Floor | King room | 0.5 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0 | 0.18182 | 0 | 0.33333 | 0 | 0.43529 | 0 | 1
323 | 3rd Floor | Suite room | 50% | 100% | 50% | 0% | 62.5% | 28.57% | 75% | 66.67% | 85.71% | 0% | 18.18% | 0% | 66.67% | 0% | 42.35% |  |  |  |  | 327 | 3rd Floor | King room | 0.5 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0 | 0.18182 | 0 | 0.66667 | 0 | 0.44706 | 0 | 1
324 | 3rd Floor | King room | 50% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 0% | 18.18% | 0% | 33.33% | 0% | 43.53% |  |  |  |  | 328 | 3rd Floor | King room | 0.5 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.75 | 0.66667 | 0.85714 | 0.33333 | 0.18182 | 0 | 0.33333 | 0 | 0.44706 | 0 | 1
325 | 3rd Floor | King room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 0% | 18.18% | 0% | 33.33% | 0% | 44.19% |  |  |  |  | 401 | 4th Floor | King room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.5 | 0.55556 | 0.85714 | 0 | 0.18182 | 0 | 0.66667 | 0 | 0.43023 | 0 | 1
326 | 3rd Floor | King room | 50% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 0% | 18.18% | 0% | 33.33% | 0% | 43.53% |  |  |  |  | 402 | 4th Floor | Twin room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.5 | 0.44444 | 0.85714 | 0.33333 | 0.18182 | 0 | 0.66667 | 0 | 0.43023 | 0 | 1
327 | 3rd Floor | King room | 50% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 0% | 18.18% | 0% | 66.67% | 0% | 44.71% |  |  |  |  | 403 | 4th Floor | King room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.5 | 0.44444 | 0.85714 | 0 | 0.18182 | 0 | 0.66667 | 0 | 0.4186 | 0 | 1
328 | 3rd Floor | King room | 50% | 100% | 50% | 0% | 62.5% | 57.14% | 75% | 66.67% | 85.71% | 33.33% | 18.18% | 0% | 33.33% | 0% | 44.71% |  |  |  |  | 404 | 4th Floor | Twin room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.14286 | 0.5 | 0.44444 | 0.85714 | 0.33333 | 0.090909 | 0 | 0.33333 | 0 | 0.37209 | 0 | 1
401 | 4th Floor | King room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 50% | 55.56% | 85.71% | 0% | 18.18% | 0% | 66.67% | 0% | 43.02% |  |  |  |  | 405 | 4th Floor | King room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.5 | 0.44444 | 0.85714 | 0 | 0.18182 | 0 | 0.66667 | 0 | 0.4186 | 0 | 1
402 | 4th Floor | Twin room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 50% | 44.44% | 85.71% | 33.33% | 18.18% | 0% | 66.67% | 0% | 43.02% |  |  |  |  | 406 | 4th Floor | King room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.5 | 0.44444 | 0.85714 | 0 | 0.18182 | 0 | 0.66667 | 0 | 0.4186 | 0 | 1
403 | 4th Floor | King room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 50% | 44.44% | 85.71% | 0% | 18.18% | 0% | 66.67% | 0% | 41.86% |  |  |  |  | 407 | 4th Floor | Twin room | 0.75 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.5 | 0.44444 | 0.85714 | 0 | 0.18182 | 0 | 0.66667 | 0 | 0.42529 | 0 | 1
404 | 4th Floor | Twin room | 66.67% | 100% | 50% | 0% | 62.5% | 14.29% | 50% | 44.44% | 85.71% | 33.33% | 9.091% | 0% | 33.33% | 0% | 37.21% |  |  |  |  | 408 | 4th Floor | King room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.25 | 0.44444 | 0.85714 | 0 | 0.18182 | 0 | 0.66667 | 0 | 0.40698 | 0 | 1
405 | 4th Floor | King room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 50% | 44.44% | 85.71% | 0% | 18.18% | 0% | 66.67% | 0% | 41.86% |  |  |  |  | 409 | 4th Floor | Twin room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.25 | 0.44444 | 0.85714 | 0 | 0.18182 | 0 | 0.66667 | 0 | 0.40698 | 0 | 1
406 | 4th Floor | King room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 50% | 44.44% | 85.71% | 0% | 18.18% | 0% | 66.67% | 0% | 41.86% |  |  |  |  | 410 | 4th Floor | King room | 0.5 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.25 | 0.44444 | 0.57143 | 0 | 0.18182 | 0 | 0 | 0 | 0.35294 | 0 | 1
407 | 4th Floor | Twin room | 75% | 100% | 50% | 0% | 62.5% | 57.14% | 50% | 44.44% | 85.71% | 0% | 18.18% | 0% | 66.67% | 0% | 42.53% |  |  |  |  | 411 | 4th Floor | King room | 0.5 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.25 | 0.44444 | 0.57143 | 0 | 0.18182 | 0 | 0.33333 | 0 | 0.36471 | 0 | 1
408 | 4th Floor | King room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 25% | 44.44% | 85.71% | 0% | 18.18% | 0% | 66.67% | 0% | 40.7% |  |  |  |  | 412 | 4th Floor | King room | 0.5 | 1 | 0.5 | 0 | 0.625 | 0.14286 | 0.25 | 0.44444 | 0.57143 | 0 | 0.18182 | 0 | 0 | 0 | 0.31765 | 0 | 1
409 | 4th Floor | Twin room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 25% | 44.44% | 85.71% | 0% | 18.18% | 0% | 66.67% | 0% | 40.7% |  |  |  |  | 413 | 4th Floor | Suite room | 0.5 | 1 | 0.5 | 0 | 0.625 | 0.14286 | 0.25 | 0.44444 | 0.57143 | 0 | 0.090909 | 0 | 0.66667 | 0 | 0.32941 | 0 | 1
410 | 4th Floor | King room | 50% | 100% | 50% | 0% | 62.5% | 57.14% | 25% | 44.44% | 57.14% | 0% | 18.18% | 0% | 0% | 0% | 35.29% |  |  |  |  | 414 | 4th Floor | King room | 0.75 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.25 | 0.44444 | 0.57143 | 0 | 0.18182 | 0 | 0 | 0 | 0.36782 | 0 | 1
411 | 4th Floor | King room | 50% | 100% | 50% | 0% | 62.5% | 57.14% | 25% | 44.44% | 57.14% | 0% | 18.18% | 0% | 33.33% | 0% | 36.47% |  |  |  |  | 415 | 4th Floor | King room | 0.66667 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.25 | 0.44444 | 0.57143 | 0 | 0.18182 | 0 | 0 | 0 | 0.36047 | 0 | 1
412 | 4th Floor | King room | 50% | 100% | 50% | 0% | 62.5% | 14.29% | 25% | 44.44% | 57.14% | 0% | 18.18% | 0% | 0% | 0% | 31.76% |  |  |  |  | 416 | 4th Floor | King room | 0.5 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.5 | 0.44444 | 0.85714 | 0.33333 | 0.18182 | 0 | 0.66667 | 0 | 0.42353 | 0 | 1
413 | 4th Floor | Suite room | 50% | 100% | 50% | 0% | 62.5% | 14.29% | 25% | 44.44% | 57.14% | 0% | 9.091% | 0% | 66.67% | 0% | 32.94% |  |  |  |  | 417 | 4th Floor | King room | 0.5 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.5 | 0.44444 | 0.85714 | 0 | 0.18182 | 0 | 0.66667 | 0 | 0.41176 | 0 | 1
414 | 4th Floor | King room | 75% | 100% | 50% | 0% | 62.5% | 57.14% | 25% | 44.44% | 57.14% | 0% | 18.18% | 0% | 0% | 0% | 36.78% |  |  |  |  | 418 | 4th Floor | King room | 0.5 | 1 | 0.5 | 0 | 0.625 | 0.57143 | 0.5 | 0.44444 | 0.85714 | 0.33333 | 0.18182 | 0 | 0.66667 | 0 | 0.42353 | 0 | 1
415 | 4th Floor | King room | 66.67% | 100% | 50% | 0% | 62.5% | 57.14% | 25% | 44.44% | 57.14% | 0% | 18.18% | 0% | 0% | 0% | 36.05%
416 | 4th Floor | King room | 50% | 100% | 50% | 0% | 62.5% | 57.14% | 50% | 44.44% | 85.71% | 33.33% | 18.18% | 0% | 66.67% | 0% | 42.35%
417 | 4th Floor | King room | 50% | 100% | 50% | 0% | 62.5% | 57.14% | 50% | 44.44% | 85.71% | 0% | 18.18% | 0% | 66.67% | 0% | 41.18%
418 | 4th Floor | King room | 50% | 100% | 50% | 0% | 62.5% | 57.14% | 50% | 44.44% | 85.71% | 33.33% | 18.18% | 0% | 66.67% | 0% | 42.35%

## PUBLIC_AREA-DASHBOARD
[21 empty] | Trade Category | Start Col | End Col | Completed | Ongoing | Not Started | Total Valid | Completion % |  | Trade Category | Completion % |  | Floor | Completed | Ongoing | Not Started |  | Floor | Completed | Ongoing | Not Started | Total Valid | Completion % | Filtered Areas
HOTEL PUBLIC AREA FIT-OUT EXECUTIVE DASHBOARD | [20 empty] | Civil Work | D | E | 88 | 20 | 8 | 116 | 0.84483 |  | Tiles & Flooring | 0 |  | Ground Floor | 404 | 64 | 1832 |  | Ground Floor | 404 | 64 | 1832 | 2300 | 0.18957 | All Day Dining Area
Real-time Milestones, Trade Completion Analytics & Area Inspection Status ¦ Data Source: PUBLIC AREA | [20 empty] | Electrical | F | P | 23 | 13 | 548 | 584 | 0.050514 |  | Electrical | 0.050514 |  | Terrace | 1 | 7 | 202 |  | Terrace | 1 | 7 | 202 | 210 | 0.021429 | Receiption Area
FLOOR FILTER |  | AREA TYPE FILTER |  | AREA INSPECTION | [16 empty] | Plumbing | Q | W | 74 | 3 | 96 | 173 | 0.43642 |  | HVAC | 0.057576 | [12 empty] | Banquet 2
All Floors |  | All Areas |  | Swimming pool Area | [16 empty] | Paint | X | AE | 71 | 4 | 316 | 391 | 0.1867 |  | Furniture Work | 0.15075 | [12 empty] | Banquet 2 Pre Function
[21 empty] | Fire Safety | AF | AK | 82 | 0 | 268 | 350 | 0.23429 |  | Paint | 0.1867 | [12 empty] | Wedding Boutique
OVERALL COMPLETION |  |  |  | AREAS 100% COMPLETE |  |  |  | PRIMARY BOTTLENECK |  |  |  | ACTIVE ONGOING (WIP) |  |  |  | TOTAL NOT STARTED | AREA INSPECTION PANEL — Swimming pool Area |  |  |  | HVAC | AL | AQ | 16 | 6 | 308 | 330 | 0.057576 |  | False Ceiling | 0.23103 | [12 empty] | Banquet 3
17.55% |  |  |  | 0 / 59 |  |  |  | Tiles & Flooring |  |  |  | 71 |  |  |  | 2034 | Floor: | Terrace | Type: | Main Area | Tiles & Flooring | AR | AU | 0 | 0 | 222 | 222 | 0 |  | Fire Safety | 0.23429 | [12 empty] | Banquet 3 Pre Function
Completed: 405 items |  |  |  | Pending: 59 Areas |  |  |  | Completion: 0.0% |  |  |  | Active Tasks across Areas |  |  |  | Tasks Pending Mobilization | Overall: | 5.714% | Status: | ON GOING | False Ceiling | AV | AX | 26 | 15 | 104 | 145 | 0.23103 |  | Plumbing | 0.43642 | [12 empty] | Conference Room
(Excludes NOT VALID items) |  |  |  | Lowest Milestone Trade |  |  |  | Requires Supervision |  |  |  | Awaiting Preceding Trades |  |  |  | Critical Path Ahead | TRADE BREAKDOWN |  |  |  | Furniture Work | AY | BB | 25 | 10 | 164 | 199 | 0.15075 |  | Civil Work | 0.84483 | [12 empty] | Owners Cabin
[17 empty] | Civil Work | 50% | ON GOING | [24 empty] | G M Office
[17 empty] | Electrical | 0% | NOT STARTED | [24 empty] | Utility Store
[17 empty] | Plumbing | 0% | NOT STARTED | [24 empty] | Male Toilet
[17 empty] | Paint | 0% | NOT STARTED | [24 empty] | Female Toilet
[17 empty] | Fire Safety | 16.67% | ON GOING | [24 empty] | BACK OFFICE
[17 empty] | HVAC | 0% | NOT STARTED |  | Overall Completion % | 0.1755 | [21 empty] | Luggage Room
[17 empty] | Tiles & Flooring | 0% | NOT STARTED |  | Total Completed | 405 | [21 empty] | Complete Passage Area
[17 empty] | False Ceiling | 0% | NOT STARTED |  | Total Ongoing | 71 | [21 empty] | Live Kitchen
[17 empty] | Furniture Work | 0% | NOT STARTED |  | Total Not Started | 2034 | [21 empty] | Dish Wash Area
[17 empty] | CHECKLIST ITEM SUMMARY |  |  |  | Bottleneck Category | Tiles & Flooring | [21 empty] | Back Kitchen
[17 empty] | Completed Items |  | 1 |  | Bottleneck Rate | 0 | [21 empty] | Pot Wash
[17 empty] | Ongoing (WIP) Items |  | 2 |  | Areas 100% Complete | 0 | [21 empty] | Veg Prep Area
[17 empty] | Not Started Items |  | 32 |  | Areas Pending | 59 | [21 empty] | Walk-In Refridgerator
[17 empty] | Not Valid (N/A) Items |  | 15 |  | Area No | Floor | Area Name | Sub-Area / Location | Civil | Electrical | Plumbing | Paint | Fire | HVAC | Tiles | Ceiling | Furniture | Total Completed | Total Ongoing | Total Not Started | Overall % | Is Complete | Include In Filter | Status | Handover Readiness |  |  | Main Store
[17 empty] | CURRENT ONGOING TASKS IN AREA |  |  |  | 1 | Ground Floor | All Day Dining Area | Main Area | 0.5 | 0.1 | 0.6 | 0 | 0.5 | 0.16667 | 0 | 0 | 0.16667 | 6 | 7 | 34 | 0.20213 | 0 | 1 | IN PROGRESS | Mobilized |  |  | IT Server Room
[17 empty] | Brickwork, Plaster |  |  |  | 2 | Ground Floor | Receiption Area | Main Area | 0.5 | 0.1 | 0 | 0 | 0.5 | 0.16667 | 0 | 0 | 0.16667 | 3 | 7 | 31 | 0.15854 | 0 | 1 | IN PROGRESS | Mobilized |  |  | Beverage Store
PUBLIC AREA × TRADE PROGRESS HEAT MATRIX ¦ LIVE WORK-IN-PROGRESS & BOTTLENECK TRACKER | [20 empty] | 3 | Ground Floor | Banquet 2 | Main Area | 1 | 0.3 | 0.8 | 0.14286 | 0.66667 | 0.33333 | 0 | 0.5 | 0.75 | 16 | 3 | 24 | 0.40698 | 0 | 1 | IN PROGRESS | Under Fit-out |  |  | HR Manager
S.No. | Area Name | Sub-Area / Location | Floor | Civil | Electrical | Plumbing | Paint | Fire | HVAC | Tiles | Ceiling | Furniture | Overall % | Status | Handover Readiness |  | NOT STARTED TASKS IN AREA |  |  |  |  | Ground Floor | Banquet 2 Pre Function | ↳ Banquet 2 Pre Function | 1 | 0.35 | 0.57143 | 0.14286 | 0.66667 | 0.33333 | 0 | 0 | 0 | 16 | 1 | 29 | 0.3587 | 0 | 1 | IN PROGRESS | Under Fit-out |  |  | Open Office
1 | All Day Dining Area | Main Area | Ground Floor | 50% | 10% | 60% | 0% | 50% | 16.67% | 0% | 0% | 16.67% | 20.21% | IN PROGRESS | Mobilized |  | Conduting , Light Wire, Switches Work, Light Fixing, Main DB / MCB Installation, Speaker Wire, CAT-6, CCTV Wire, Wi-Fi Cable, EPABX + Wi-Fi + CCTV , Music / PA System, Final Testing, Wall Punning, Putty1, Putty2, Primer, Paint 1, Paint 2, Final Paint Touchup, Fire Alarm Cable, Fire Alarm System, Sprinklers, Pipeline Testing, Speakers / Sounder, Smoke Detecters, Final Testing, AHU / Outdoors Placement, Final Testing, Floor tiles, Skirting, Framing Work, Board Fixing |  |  |  | 4 | Ground Floor | Wedding Boutique | Main Area | 1 | 0.2 | 0.66667 | 0.14286 | 0.5 | 0.16667 | 0 | 0 | 0 | 11 | 0 | 32 | 0.25581 | 0 | 1 | IN PROGRESS | Under Fit-out |  |  | Record Room
2 | Receiption Area | Main Area | Ground Floor | 50% | 10% | 0% | 0% | 50% | 16.67% | 0% | 0% | 16.67% | 15.85% | IN PROGRESS | Mobilized | [5 empty] | 5 | Ground Floor | Banquet 3 | Main Area | 1 | 0.2 | 0.4 | 0.14286 | 0.5 | 0.25 | 0 | 1 | 0.75 | 13 | 2 | 28 | 0.32558 | 0 | 1 | IN PROGRESS | Under Fit-out |  |  | Account Manager
3 | Banquet 2 | Main Area | Ground Floor | 100% | 30% | 80% | 14.29% | 66.67% | 33.33% | 0% | 50% | 75% | 40.7% | IN PROGRESS | Under Fit-out | [6 empty] | Ground Floor | Banquet 3 Pre Function | ↳ Banquet 3 Pre Function | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 0 | 1 | NOT STARTED | Pending Start |  |  | Meeting Room
| Banquet 2 Pre Function | ↳ Banquet 2 Pre Function | Ground Floor | 100% | 35% | 57.14% | 14.29% | 66.67% | 33.33% | 0% | 0% | 0% | 35.87% | IN PROGRESS | Under Fit-out | [5 empty] | 6 | Ground Floor | Conference Room | Main Area | 1 | 0.2 | 0 | 0.14286 | 0.33333 | 0 | 0 | 0.5 | 0 | 8 | 0 | 33 | 0.19512 | 0 | 1 | IN PROGRESS | Mobilized |  |  | Bakery
4 | Wedding Boutique | Main Area | Ground Floor | 100% | 20% | 66.67% | 14.29% | 50% | 16.67% | 0% | 0% | 0% | 25.58% | IN PROGRESS | Under Fit-out | [5 empty] | 7 | Ground Floor | Owners Cabin | Main Area | 1 | 0.2 | 0 | 0.14286 | 0.33333 | 0 | 0 | 0 | 0 | 7 | 0 | 36 | 0.16279 | 0 | 1 | IN PROGRESS | Mobilized |  |  | Walkin Refridgerator
5 | Banquet 3 | Main Area | Ground Floor | 100% | 20% | 40% | 14.29% | 50% | 25% | 0% | 100% | 75% | 32.56% | IN PROGRESS | Under Fit-out | [5 empty] | 8 | Ground Floor | G M Office | Main Area | 1 | 0 | 0 | 0.14286 | 0.16667 | 0 | 0 | 0 | 0 | 4 | 0 | 39 | 0.093023 | 0 | 1 | IN PROGRESS | Mobilized |  |  | Room Service
| Banquet 3 Pre Function | ↳ Banquet 3 Pre Function | Ground Floor | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | NOT STARTED | Pending Start | [5 empty] | 9 | Ground Floor | Utility Store | Main Area | 1 | 0 | 0 | 0.14286 | 0.16667 | 0 | 0 | 0 | 0 | 4 | 0 | 39 | 0.093023 | 0 | 1 | IN PROGRESS | Mobilized |  |  | Cafetaria
6 | Conference Room | Main Area | Ground Floor | 100% | 20% | 0% | 14.29% | 33.33% | 0% | 0% | 50% | 0% | 19.51% | IN PROGRESS | Mobilized | [5 empty] | 10 | Ground Floor | Male Toilet | Main Area | 1 | 0.2 | 0.64286 | 0 | 0.33333 | 0 | 0 | 0.16667 | 0.33333 | 10 | 4 | 33 | 0.25532 | 0 | 1 | IN PROGRESS | Under Fit-out |  |  | Staff Dish Wash
7 | Owners Cabin | Main Area | Ground Floor | 100% | 20% | 0% | 14.29% | 33.33% | 0% | 0% | 0% | 0% | 16.28% | IN PROGRESS | Mobilized | [5 empty] | 11 | Ground Floor | Female Toilet | Main Area | 1 | 0.2 | 0.71429 | 0 | 0.33333 | 0 | 0 | 0.16667 | 0.16667 | 11 | 2 | 34 | 0.25532 | 0 | 1 | IN PROGRESS | Under Fit-out |  |  | Laundry Area
8 | G M Office | Main Area | Ground Floor | 100% | 0% | 0% | 14.29% | 16.67% | 0% | 0% | 0% | 0% | 9.302% | IN PROGRESS | Mobilized | [5 empty] | 12 | Ground Floor | BACK OFFICE | Main Area | 1 | 0 | 0 | 0 | 0.16667 | 0 | 0 | 0 | 0 | 3 | 0 | 42 | 0.066667 | 0 | 1 | IN PROGRESS | Mobilized |  |  | Electrical Panel Room
9 | Utility Store | Main Area | Ground Floor | 100% | 0% | 0% | 14.29% | 16.67% | 0% | 0% | 0% | 0% | 9.302% | IN PROGRESS | Mobilized | [6 empty] | Ground Floor | Luggage Room | ↳ Luggage Room | 1 | 0 | 0 | 0.14286 | 0.2 | 0 | 0 | 0 | 0.125 | 4 | 1 | 37 | 0.10714 | 0 | 1 | IN PROGRESS | Mobilized |  |  | Chief Engg. Manger
10 | Male Toilet | Main Area | Ground Floor | 100% | 20% | 64.29% | 0% | 33.33% | 0% | 0% | 16.67% | 33.33% | 25.53% | IN PROGRESS | Under Fit-out | [5 empty] | 13 | Ground Floor | Complete Passage Area | Main Area | 1 | 0.2 | 0.66667 | 0.14286 | 0.33333 | 0 | 0 | 0 | 0.5 | 11 | 0 | 34 | 0.24444 | 0 | 1 | IN PROGRESS | Mobilized |  |  | Engineerng Store
11 | Female Toilet | Main Area | Ground Floor | 100% | 20% | 71.43% | 0% | 33.33% | 0% | 0% | 16.67% | 16.67% | 25.53% | IN PROGRESS | Under Fit-out | [5 empty] | 14 | Ground Floor | Live Kitchen | Main Area | 1 | 0 | 0.66667 | 0.28571 | 0.16667 | 0.16667 | 0 | 0.75 | 0 | 11 | 1 | 35 | 0.24468 | 0 | 1 | IN PROGRESS | Mobilized |  |  | Garbage Area
12 | BACK OFFICE | Main Area | Ground Floor | 100% | 0% | 0% | 0% | 16.67% | 0% | 0% | 0% | 0% | 6.667% | IN PROGRESS | Mobilized | [5 empty] | 15 | Ground Floor | Dish Wash Area | Main Area | 1 | 0 | 0.8 | 0.42857 | 0.16667 | 0 | 0 | 0 | 0 | 10 | 0 | 36 | 0.21739 | 0 | 1 | IN PROGRESS | Mobilized |  |  | Receving Area
| Luggage Room | ↳ Luggage Room | Ground Floor | 100% | 0% | 0% | 14.29% | 20% | 0% | 0% | 0% | 12.5% | 10.71% | IN PROGRESS | Mobilized | [5 empty] | 16 | Ground Floor | Back Kitchen | Main Area | 1 | 0 | 0.8 | 0.42857 | 0.16667 | 0 | 0 | 1 | 0 | 12 | 0 | 34 | 0.26087 | 0 | 1 | IN PROGRESS | Under Fit-out |  |  | CCTV Room
13 | Complete Passage Area | Main Area | Ground Floor | 100% | 20% | 66.67% | 14.29% | 33.33% | 0% | 0% | 0% | 50% | 24.44% | IN PROGRESS | Mobilized | [5 empty] | 17 | Ground Floor | Pot Wash | Main Area | 1 | 0 | 0.8 | 0.28571 | 0.16667 | 0 | 0 | 0 | 0 | 8 | 2 | 35 | 0.2 | 0 | 1 | IN PROGRESS | Mobilized |  |  | Security office
14 | Live Kitchen | Main Area | Ground Floor | 100% | 0% | 66.67% | 28.57% | 16.67% | 16.67% | 0% | 75% | 0% | 24.47% | IN PROGRESS | Mobilized | [5 empty] | 18 | Ground Floor | Veg Prep Area | Main Area | 1 | 0 | 0.8 | 0.35714 | 0.16667 | 0.16667 | 0 | 0.75 | 0 | 11 | 2 | 32 | 0.26667 | 0 | 1 | IN PROGRESS | Under Fit-out |  |  | Service Left Area
15 | Dish Wash Area | Main Area | Ground Floor | 100% | 0% | 80% | 42.86% | 16.67% | 0% | 0% | 0% | 0% | 21.74% | IN PROGRESS | Mobilized | [5 empty] | 19 | Ground Floor | Walk-In Refridgerator | Main Area | 1 | 0 | 0 | 0.42857 | 0.16667 | 0 | 0 | 0.5 | 0.25 | 8 | 0 | 33 | 0.19512 | 0 | 1 | IN PROGRESS | Mobilized |  |  | Banquet 1 Area
16 | Back Kitchen | Main Area | Ground Floor | 100% | 0% | 80% | 42.86% | 16.67% | 0% | 0% | 100% | 0% | 26.09% | IN PROGRESS | Under Fit-out | [5 empty] | 20 | Ground Floor | Main Store | Main Area | 1 | 0 | 0 | 0.42857 | 0.16667 | 0 | 0 | 0.5 | 0.25 | 8 | 0 | 34 | 0.19048 | 0 | 1 | IN PROGRESS | Mobilized |  |  | Banquet Spill Out
17 | Pot Wash | Main Area | Ground Floor | 100% | 0% | 80% | 28.57% | 16.67% | 0% | 0% | 0% | 0% | 20% | IN PROGRESS | Mobilized | [5 empty] | 21 | Ground Floor | IT Server Room | Main Area | 1 | 0 | 0 | 0.42857 | 0.16667 | 0 | 0 | 0.5 | 0 | 7 | 0 | 34 | 0.17073 | 0 | 1 | IN PROGRESS | Mobilized |  |  | Pre Function
18 | Veg Prep Area | Main Area | Ground Floor | 100% | 0% | 80% | 35.71% | 16.67% | 16.67% | 0% | 75% | 0% | 26.67% | IN PROGRESS | Under Fit-out | [5 empty] | 22 | Ground Floor | Beverage Store | Main Area | 1 | 0 | 0 | 0.42857 | 0.16667 | 0 | 0 | 0.5 | 0 | 7 | 0 | 34 | 0.17073 | 0 | 1 | IN PROGRESS | Mobilized |  |  | Passage Entry
19 | Walk-In Refridgerator | Main Area | Ground Floor | 100% | 0% | 0% | 42.86% | 16.67% | 0% | 0% | 50% | 25% | 19.51% | IN PROGRESS | Mobilized | [5 empty] | 23 | Ground Floor | HR Manager | Main Area | 1 | 0 | 0 | 0.42857 | 0.33333 | 0 | 0 | 0.16667 | 0.25 | 8 | 1 | 34 | 0.19767 | 0 | 1 | IN PROGRESS | Mobilized |  |  | Male Toilet
20 | Main Store | Main Area | Ground Floor | 100% | 0% | 0% | 42.86% | 16.67% | 0% | 0% | 50% | 25% | 19.05% | IN PROGRESS | Mobilized | [6 empty] | Ground Floor | Open Office | ↳ Open Office | 1 | 0 | 0 | 0.42857 | 0.16667 | 0 | 0 | 0.16667 | 0.25 | 7 | 1 | 35 | 0.17442 | 0 | 1 | IN PROGRESS | Mobilized |  |  | Female Toilet
21 | IT Server Room | Main Area | Ground Floor | 100% | 0% | 0% | 42.86% | 16.67% | 0% | 0% | 50% | 0% | 17.07% | IN PROGRESS | Mobilized | [6 empty] | Ground Floor | Record Room | ↳ Record Room | 1 | 0 | 0 | 0.42857 | 0.16667 | 0 | 0 | 0.16667 | 0.25 | 7 | 1 | 35 | 0.17442 | 0 | 1 | IN PROGRESS | Mobilized |  |  | Banquet Furniture Store
22 | Beverage Store | Main Area | Ground Floor | 100% | 0% | 0% | 42.86% | 16.67% | 0% | 0% | 50% | 0% | 17.07% | IN PROGRESS | Mobilized | [6 empty] | Ground Floor | Account Manager | ↳ Account Manager | 1 | 0 | 0 | 0.42857 | 0.16667 | 0 | 0 | 0.16667 | 0.25 | 7 | 1 | 34 | 0.17857 | 0 | 1 | IN PROGRESS | Mobilized |  |  | Banquet Dish wash
23 | HR Manager | Main Area | Ground Floor | 100% | 0% | 0% | 42.86% | 33.33% | 0% | 0% | 16.67% | 25% | 19.77% | IN PROGRESS | Mobilized | [5 empty] | 24 | Ground Floor | Meeting Room | Main Area | 1 | 0 | 0 | 0.42857 | 0.16667 | 0 | 0 | 0.25 | 0.25 | 7 | 1 | 34 | 0.17857 | 0 | 1 | IN PROGRESS | Mobilized |  |  | main Kitchen
| Open Office | ↳ Open Office | Ground Floor | 100% | 0% | 0% | 42.86% | 16.67% | 0% | 0% | 16.67% | 25% | 17.44% | IN PROGRESS | Mobilized | [5 empty] | 25 | Ground Floor | Bakery | Main Area | 1 | 0 | 0.57143 | 0.14286 | 0.16667 | 0 | 0 | 0 | 0.25 | 9 | 0 | 40 | 0.18367 | 0 | 1 | IN PROGRESS | Mobilized |  |  | Swimming pool Area
| Record Room | ↳ Record Room | Ground Floor | 100% | 0% | 0% | 42.86% | 16.67% | 0% | 0% | 16.67% | 25% | 17.44% | IN PROGRESS | Mobilized | [6 empty] | Ground Floor | Walkin Refridgerator | ↳ Walkin Refridgerator | 1 | 0 | 0 | 0.14286 | 0.33333 | 0.16667 | 0 | 0 | 0.25 | 7 | 0 | 36 | 0.16279 | 0 | 1 | IN PROGRESS | Mobilized |  |  | Deck Area
| Account Manager | ↳ Account Manager | Ground Floor | 100% | 0% | 0% | 42.86% | 16.67% | 0% | 0% | 16.67% | 25% | 17.86% | IN PROGRESS | Mobilized | [5 empty] | 26 | Ground Floor | Room Service | Main Area | 1 | 0 | 0 | 0.42857 | 0.33333 | 0.16667 | 0 | 0.66667 | 0.25 | 11 | 0 | 32 | 0.25581 | 0 | 1 | IN PROGRESS | Under Fit-out |  |  | Gym
24 | Meeting Room | Main Area | Ground Floor | 100% | 0% | 0% | 42.86% | 16.67% | 0% | 0% | 25% | 25% | 17.86% | IN PROGRESS | Mobilized | [5 empty] | 27 | Ground Floor | Cafetaria | Main Area | 1 | 0 | 0.8 | 0.42857 | 0.33333 | 0 | 0 | 0.66667 | 0.25 | 14 | 0 | 33 | 0.29787 | 0 | 1 | IN PROGRESS | Under Fit-out |  |  | Male Changing Room
25 | Bakery | Main Area | Ground Floor | 100% | 0% | 57.14% | 14.29% | 16.67% | 0% | 0% | 0% | 25% | 18.37% | IN PROGRESS | Mobilized | [6 empty] | Ground Floor | Staff Dish Wash | ↳ Staff Dish Wash | 1 | 0 | 0.57143 | 0.42857 | 0.33333 | 0.16667 | 0 | 0.66667 | 0.25 | 15 | 0 | 34 | 0.30612 | 0 | 1 | IN PROGRESS | Under Fit-out |  |  | Female Chaning Room
| Walkin Refridgerator | ↳ Walkin Refridgerator | Ground Floor | 100% | 0% | 0% | 14.29% | 33.33% | 16.67% | 0% | 0% | 25% | 16.28% | IN PROGRESS | Mobilized | [5 empty] | 28 | Ground Floor | Laundry Area | Main Area | 0.5 | 0 | 0.57143 | 0.14286 | 0.33333 | 0 | 0 | 0.33333 | 0.25 | 8 | 4 | 36 | 0.20833 | 0 | 1 | IN PROGRESS | Mobilized |  |  | RAIN DANCE
26 | Room Service | Main Area | Ground Floor | 100% | 0% | 0% | 42.86% | 33.33% | 16.67% | 0% | 66.67% | 25% | 25.58% | IN PROGRESS | Under Fit-out | [5 empty] | 29 | Ground Floor | Electrical Panel Room | Main Area | 1 | 0 | 0 | 0.16667 | 0.33333 | 0.083333 | 0 | 0.16667 | 0.25 | 6 | 2 | 34 | 0.16667 | 0 | 1 | IN PROGRESS | Mobilized
27 | Cafetaria | Main Area | Ground Floor | 100% | 0% | 80% | 42.86% | 33.33% | 0% | 0% | 66.67% | 25% | 29.79% | IN PROGRESS | Under Fit-out | [6 empty] | Ground Floor | Chief Engg. Manger | ↳ Chief Engg. Manger | 1 | 0 | 0 | 0.16667 | 0.33333 | 0 | 0 | 0 | 0.25 | 6 | 0 | 36 | 0.14286 | 0 | 1 | IN PROGRESS | Mobilized
| Staff Dish Wash | ↳ Staff Dish Wash | Ground Floor | 100% | 0% | 57.14% | 42.86% | 33.33% | 16.67% | 0% | 66.67% | 25% | 30.61% | IN PROGRESS | Under Fit-out | [6 empty] | Ground Floor | Engineerng Store | ↳ Engineerng Store | 1 | 0 | 0 | 0.16667 | 0.33333 | 0 | 0 | 0.16667 | 0.25 | 6 | 1 | 35 | 0.15476 | 0 | 1 | IN PROGRESS | Mobilized
28 | Laundry Area | Main Area | Ground Floor | 50% | 0% | 57.14% | 14.29% | 33.33% | 0% | 0% | 33.33% | 25% | 20.83% | IN PROGRESS | Mobilized | [5 empty] | 30 | Ground Floor | Garbage Area | Main Area | 1 | 0 | 0 | 0.25 | 0.16667 | 0 | 0 | 1 | 0.25 | 7 | 0 | 32 | 0.17949 | 0 | 1 | IN PROGRESS | Mobilized
29 | Electrical Panel Room | Main Area | Ground Floor | 100% | 0% | 0% | 16.67% | 33.33% | 8.333% | 0% | 16.67% | 25% | 16.67% | IN PROGRESS | Mobilized | [5 empty] | 31 | Ground Floor | Receving Area | Main Area | 1 | 0 | 0 | 0.5 | 0.16667 | 0 | 0 | 1 | 0.25 | 9 | 0 | 32 | 0.21951 | 0 | 1 | IN PROGRESS | Mobilized
| Chief Engg. Manger | ↳ Chief Engg. Manger | Ground Floor | 100% | 0% | 0% | 16.67% | 33.33% | 0% | 0% | 0% | 25% | 14.29% | IN PROGRESS | Mobilized | [5 empty] | 32 | Ground Floor | CCTV Room | Main Area | 1 | 0.090909 | 0 | 0.2 | 0.16667 | 0 | 0 | 0.5 | 0.25 | 7 | 0 | 34 | 0.17073 | 0 | 1 | IN PROGRESS | Mobilized
| Engineerng Store | ↳ Engineerng Store | Ground Floor | 100% | 0% | 0% | 16.67% | 33.33% | 0% | 0% | 16.67% | 25% | 15.48% | IN PROGRESS | Mobilized | [5 empty] | 33 | Ground Floor | Security office | Main Area | 1 | 0.090909 | 0 | 0.2 | 0.16667 | 0 | 0 | 0.5 | 0.25 | 7 | 0 | 34 | 0.17073 | 0 | 1 | IN PROGRESS | Mobilized
30 | Garbage Area | Main Area | Ground Floor | 100% | 0% | 0% | 25% | 16.67% | 0% | 0% | 100% | 25% | 17.95% | IN PROGRESS | Mobilized | [5 empty] | 34 | Ground Floor | Service Left Area | Main Area | 1 | 0 | 0 | 0 | 0.16667 | 0 | 0 | 0 | 0 | 3 | 0 | 35 | 0.078947 | 0 | 1 | IN PROGRESS | Mobilized
31 | Receving Area | Main Area | Ground Floor | 100% | 0% | 0% | 50% | 16.67% | 0% | 0% | 100% | 25% | 21.95% | IN PROGRESS | Mobilized | [5 empty] | 35 | Ground Floor | Banquet 1 Area | Main Area | 0.75 | 0.1 | 0 | 0.14286 | 0.16667 | 0.33333 | 0 | 0.5 | 0.33333 | 6 | 5 | 30 | 0.20732 | 0 | 1 | IN PROGRESS | Mobilized
32 | CCTV Room | Main Area | Ground Floor | 100% | 9.091% | 0% | 20% | 16.67% | 0% | 0% | 50% | 25% | 17.07% | IN PROGRESS | Mobilized | [6 empty] | Ground Floor | Banquet Spill Out | ↳ Banquet Spill Out | 0.75 | 0.2 | 0 | 0.083333 | 0.33333 | 0.33333 | 0 | 0.25 | 0.33333 | 8 | 3 | 29 | 0.2375 | 0 | 1 | IN PROGRESS | Mobilized
33 | Security office | Main Area | Ground Floor | 100% | 9.091% | 0% | 20% | 16.67% | 0% | 0% | 50% | 25% | 17.07% | IN PROGRESS | Mobilized | [6 empty] | Ground Floor | Pre Function | ↳ Pre Function | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41 | 0 | 0 | 1 | NOT STARTED | Pending Start
34 | Service Left Area | Main Area | Ground Floor | 100% | 0% | 0% | 0% | 16.67% | 0% | 0% | 0% | 0% | 7.895% | IN PROGRESS | Mobilized | [6 empty] | Ground Floor | Passage Entry | ↳ Passage Entry | 0.75 | 0 | 0 | 0.16667 | 0.33333 | 0.16667 | 0 | 0 | 0 | 5 | 1 | 35 | 0.13415 | 0 | 1 | IN PROGRESS | Mobilized
35 | Banquet 1 Area | Main Area | Ground Floor | 75% | 10% | 0% | 14.29% | 16.67% | 33.33% | 0% | 50% | 33.33% | 20.73% | IN PROGRESS | Mobilized | [6 empty] | Ground Floor | Male Toilet | ↳ Male Toilet | 0.75 | 0.1 | 0.64286 | 0 | 0.16667 | 0 | 0 | 0 | 0 | 6 | 4 | 38 | 0.16667 | 0 | 1 | IN PROGRESS | Mobilized
| Banquet Spill Out | ↳ Banquet Spill Out | Ground Floor | 75% | 20% | 0% | 8.333% | 33.33% | 33.33% | 0% | 25% | 33.33% | 23.75% | IN PROGRESS | Mobilized | [6 empty] | Ground Floor | Female Toilet | ↳ Female Toilet | 0.75 | 0.1 | 0.64286 | 0 | 0.16667 | 0 | 0 | 0 | 0 | 6 | 4 | 38 | 0.16667 | 0 | 1 | IN PROGRESS | Mobilized
| Pre Function | ↳ Pre Function | Ground Floor | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | NOT STARTED | Pending Start | [6 empty] | Ground Floor | Banquet Furniture Store | ↳ Banquet Furniture Store | 0.5 | 0 | 0 | 0 | 0.16667 | 0 | 0 | 0.5 | 0 | 2 | 2 | 36 | 0.075 | 0 | 1 | IN PROGRESS | Mobilized
| Passage Entry | ↳ Passage Entry | Ground Floor | 75% | 0% | 0% | 16.67% | 33.33% | 16.67% | 0% | 0% | 0% | 13.41% | IN PROGRESS | Mobilized | [6 empty] | Ground Floor | Banquet Dish wash | ↳ Banquet Dish wash | 1 | 0 | 0 | 0 | 0.16667 | 0 | 0 | 0.33333 | 0 | 4 | 0 | 38 | 0.095238 | 0 | 1 | IN PROGRESS | Mobilized
| Male Toilet | ↳ Male Toilet | Ground Floor | 75% | 10% | 64.29% | 0% | 16.67% | 0% | 0% | 0% | 0% | 16.67% | IN PROGRESS | Mobilized | [6 empty] | Ground Floor | main Kitchen | ↳ main Kitchen | 1 | 0 | 0.66667 | 0 | 0.16667 | 0 | 0 | 0.16667 | 0 | 7 | 1 | 35 | 0.17442 | 0 | 1 | IN PROGRESS | Mobilized
| Female Toilet | ↳ Female Toilet | Ground Floor | 75% | 10% | 64.29% | 0% | 16.67% | 0% | 0% | 0% | 0% | 16.67% | IN PROGRESS | Mobilized | [5 empty] | 36 | Terrace | Swimming pool Area | Main Area | 0.5 | 0 | 0 | 0 | 0.16667 | 0 | 0 | 0 | 0 | 1 | 2 | 32 | 0.057143 | 0 | 1 | IN PROGRESS | Mobilized
| Banquet Furniture Store | ↳ Banquet Furniture Store | Ground Floor | 50% | 0% | 0% | 0% | 16.67% | 0% | 0% | 50% | 0% | 7.5% | IN PROGRESS | Mobilized | [6 empty] | Terrace | Deck Area | ↳ Deck Area | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 35 | 0.013889 | 0 | 1 | IN PROGRESS | Mobilized
| Banquet Dish wash | ↳ Banquet Dish wash | Ground Floor | 100% | 0% | 0% | 0% | 16.67% | 0% | 0% | 33.33% | 0% | 9.524% | IN PROGRESS | Mobilized | [6 empty] | Terrace | Gym | ↳ Gym | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 36 | 0.013514 | 0 | 1 | IN PROGRESS | Mobilized
| main Kitchen | ↳ main Kitchen | Ground Floor | 100% | 0% | 66.67% | 0% | 16.67% | 0% | 0% | 16.67% | 0% | 17.44% | IN PROGRESS | Mobilized | [6 empty] | Terrace | Male Changing Room | ↳ Male Changing Room | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 41 | 0.011905 | 0 | 1 | IN PROGRESS | Mobilized
36 | Swimming pool Area | Main Area | Terrace | 50% | 0% | 0% | 0% | 16.67% | 0% | 0% | 0% | 0% | 5.714% | IN PROGRESS | Mobilized | [6 empty] | Terrace | Female Chaning Room | ↳ Female Chaning Room | 0.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 37 | 0.013158 | 0 | 1 | IN PROGRESS | Mobilized
| Deck Area | ↳ Deck Area | Terrace | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.389% | IN PROGRESS | Mobilized | [5 empty] | 37 | Terrace | RAIN DANCE | Main Area | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 21 | 0.022727 | 0 | 1 | IN PROGRESS | Mobilized
| Gym | ↳ Gym | Terrace | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.351% | IN PROGRESS | Mobilized
| Male Changing Room | ↳ Male Changing Room | Terrace | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.19% | IN PROGRESS | Mobilized
| Female Chaning Room | ↳ Female Chaning Room | Terrace | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.316% | IN PROGRESS | Mobilized
37 | RAIN DANCE | Main Area | Terrace | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.273% | IN PROGRESS | Mobilized

## PASSAGE_DASHBOARD
[23 empty] | Trade Category | Start Col | End Col | Completed | Ongoing | Not Started | Total Valid | Completion % |  | Trade Category | Completion % |  | Floor | Completed | Ongoing | Not Started | Total Valid | Completion %
HOTEL PASSAGE FIT-OUT EXECUTIVE DASHBOARD | [22 empty] | Civil Work | C | D | 43 | 3 | 1 | 47 | 0.94681 |  | Testing | 0 |  | Ground Floor | 24 | 11 | 191 | 226 | 0.13053
Real-time Milestones, Trade Completion Analytics & Passage Inspection Status ¦ Data Source: PASSAGE | [22 empty] | Electrical | E | N | 65 | 5 | 150 | 220 | 0.30682 |  | Paint | 0.12338 |  | 1st Floor | 50 | 1 | 63 | 114 | 0.44298
FLOOR FILTER |  |  | PASSAGE INSPECTION | [19 empty] | Plumbing | O | P | 4 | 2 | 4 | 10 | 0.5 |  | Tiles & Flooring | 0.20455 |  | 2nd Floor | 44 | 0 | 69 | 113 | 0.38938
All Floors |  |  | LOUNDRY AREA PASSAGE | [19 empty] | Paint | Q | W | 18 | 2 | 134 | 154 | 0.12338 |  | HVAC | 0.21818 |  | 3rd Floor | 45 | 0 | 69 | 114 | 0.39474
[23 empty] | Fire Safety | X | AB | 34 | 5 | 71 | 110 | 0.33182 |  | False Ceiling | 0.2549 |  | 4th Floor | 33 | 6 | 75 | 114 | 0.31579
OVERALL COMPLETION |  |  | PASSAGES 100% COMPLETE |  |  |  | PRIMARY BOTTLENECK |  |  |  | ACTIVE ONGOING (WIP) |  |  |  | TOTAL NOT STARTED | [7 empty] | HVAC | AC | AG | 24 | 0 | 86 | 110 | 0.21818 |  | Electrical | 0.30682 |  | Service Areas / Stairs | 15 | 6 | 117 | 138 | 0.13043
27.23% |  |  | 0 / 24 |  |  |  | Testing |  |  |  | 24 |  |  |  | 584 |  |  | PASSAGE INSPECTION PANEL — LOUNDRY AREA PASSAGE |  |  |  |  | Tiles & Flooring | AH | AL | 12 | 3 | 51 | 66 | 0.20455 |  | Fire Safety | 0.33182
Completed: 211 items |  |  | Pending: 24 Passages |  |  |  | Completion: 0.0% |  |  |  | Active Tasks across Passages |  |  |  | Tasks Pending Mobilization |  |  | Floor: | Ground Floor |  | Passage: | LOUNDRY AREA PASSAGE | False Ceiling | AM | AO | 11 | 4 | 36 | 51 | 0.2549 |  | Plumbing | 0.5
(Excludes NOT VALID items) |  |  | Handover Milestone |  |  |  | Lowest Milestone Trade |  |  |  | Requires Supervision |  |  |  | Awaiting Preceding Trades |  |  | Overall: | 25% |  | Status: | ON GOING | Testing | AP | AR | 0 | 0 | 51 | 51 | 0 |  | Civil Work | 0.94681
TRADE BREAKDOWN
[18 empty] | Civil Work |  | 100% | COMPLETED
[18 empty] | Electrical |  | 0% | NOT STARTED
[18 empty] | Plumbing |  | 0% | NOT STARTED |  | Summary Metric | Value
[18 empty] | Paint |  | 0% | NOT STARTED |  | Total Valid Items | 819
[18 empty] | Fire Safety |  | 0% | NOT STARTED |  | Overall Completion % | 0.27228
[18 empty] | HVAC |  | 0% | NOT STARTED |  | Total Completed | 211
[18 empty] | Tiles & Flooring |  | 0% | NOT STARTED |  | Total Ongoing | 24
[18 empty] | False Ceiling |  | 0% | NOT STARTED |  | Total Not Started | 584
[18 empty] | Testing |  | 0% | NOT STARTED |  | Bottleneck Category | Testing
[18 empty] | CHECKLIST ITEM SUMMARY |  |  |  |  | Bottleneck Completion % | 0
[18 empty] | Completed Items |  |  | 2 |  | 100% Completed Passages | 0
[18 empty] | Ongoing (WIP) Items |  |  | 0 |  | Total Passages Filtered | 24
[18 empty] | Not Started Items |  |  | 6 |  | Passage Area | Floor | Civil Work | Electrical | Plumbing | Paint | Fire Safety | HVAC | Tiles & Flooring | False Ceiling | Testing | Total Completed | Total Ongoing | Total Not Started | Overall % | Is Complete | Status | Readiness | Include In Filter
[18 empty] | Not Valid (N/A) Items |  |  | 2 |  | LOUNDRY AREA PASSAGE | Ground Floor | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 6 | 0.25 | 0 | IN PROGRESS | Mobilized | 1
PASSAGE FIT-OUT × TRADE PROGRESS HEAT MATRIX ¦ LIVE WORK-IN-PROGRESS & SITE REGISTER | [17 empty] | CURRENT ONGOING TASKS IN PASSAGE |  |  |  |  | CAFETERIA PASSAGE | Ground Floor | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 6 | 0.25 | 0 | IN PROGRESS | Mobilized | 1
S.No. | Passage Area | Floor | Civil | Electrical | Plumbing | Paint | Fire | HVAC | Tiles | Ceiling | Testing | Done | WIP | Pending | Overall % | Status | Readiness | None - No ongoing tasks |  |  |  |  | BANQUATE-1 PASAGE | Ground Floor | 0.5 | 0.1 | 0 | 0 | 0.4 | 0 | 0 | 0 | 0 | 3 | 2 | 37 | 0.095238 | 0 | IN PROGRESS | Mobilized | 1
1 | LOUNDRY AREA PASSAGE | Ground Floor | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2 | 0 | 6 | 25% | IN PROGRESS | Mobilized | [5 empty] | MAIN KITCHEN PASAGE | Ground Floor | 0.25 | 0 | 0.5 | 0 | 0.1 | 0 | 0 | 0 | 0 | 0 | 4 | 38 | 0.047619 | 0 | IN PROGRESS | Mobilized | 1
2 | CAFETERIA PASSAGE | Ground Floor | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2 | 0 | 6 | 25% | IN PROGRESS | Mobilized | NOT STARTED TASKS IN PASSAGE |  |  |  |  | BANQUATE 3 PASSAGE | Ground Floor | 1 | 0.2 | 1 | 0.071429 | 0.4 | 0 | 0 | 0 | 0 | 8 | 1 | 33 | 0.20238 | 0 | IN PROGRESS | Mobilized | 1
3 | BANQUATE-1 PASAGE | Ground Floor | 50% | 10% | 0% | 0% | 40% | 0% | 0% | 0% | 0% | 3 | 2 | 37 | 9.524% | IN PROGRESS | Mobilized | Conduting , CABLE TRAY, CAT-6, SPEAKER WIRE, ALARM WIRE, ARMT CABLE |  |  |  |  | RECEPTION PASSAGE | Ground Floor | 1 | 0.15 | 0 | 0.071429 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 37 | 0.095238 | 0 | IN PROGRESS | Mobilized | 1
4 | MAIN KITCHEN PASAGE | Ground Floor | 25% | 0% | 50% | 0% | 10% | 0% | 0% | 0% | 0% | 0 | 4 | 38 | 4.762% | IN PROGRESS | Mobilized | [5 empty] | CABINE PASSAGE | Ground Floor | 1 | 0.15 | 1 | 0.14286 | 0.1 | 0 | 0 | 0 | 0 | 6 | 2 | 34 | 0.16667 | 0 | IN PROGRESS | Mobilized | 1
5 | BANQUATE 3 PASSAGE | Ground Floor | 100% | 20% | 100% | 7.143% | 40% | 0% | 0% | 0% | 0% | 8 | 1 | 33 | 20.24% | IN PROGRESS | Mobilized | [5 empty] | 1st Floor - PASSAGE A | 1st Floor | 1 | 0.6 | 0 | 0.14286 | 0.6 | 0.4 | 0.33333 | 0.66667 | 0 | 17 | 0 | 21 | 0.44737 | 0 | IN PROGRESS | Mobilized | 1
6 | RECEPTION PASSAGE | Ground Floor | 100% | 15% | 0% | 7.143% | 0% | 0% | 0% | 0% | 0% | 3 | 2 | 37 | 9.524% | IN PROGRESS | Mobilized | [5 empty] | 1st Floor - PASSAGE B | 1st Floor | 1 | 0.6 | 0 | 0.14286 | 0.6 | 0.4 | 0.33333 | 0.66667 | 0 | 17 | 0 | 21 | 0.44737 | 0 | IN PROGRESS | Mobilized | 1
7 | CABINE PASSAGE | Ground Floor | 100% | 15% | 100% | 14.29% | 10% | 0% | 0% | 0% | 0% | 6 | 2 | 34 | 16.67% | IN PROGRESS | Mobilized | [5 empty] | 1st Floor - PASSAGE C | 1st Floor | 1 | 0.6 | 0 | 0.14286 | 0.6 | 0.4 | 0.33333 | 0.5 | 0 | 16 | 1 | 21 | 0.43421 | 0 | IN PROGRESS | Mobilized | 1
8 | 1st Floor - PASSAGE A | 1st Floor | 100% | 60% | 0% | 14.29% | 60% | 40% | 33.33% | 66.67% | 0% | 17 | 0 | 21 | 44.74% | IN PROGRESS | Mobilized | [5 empty] | 2nd Floor - PASSAGE A | 2nd Floor | 1 | 0.5 | 0 | 0.14286 | 0.6 | 0.4 | 0.33333 | 0.33333 | 0 | 15 | 0 | 23 | 0.39474 | 0 | IN PROGRESS | Mobilized | 1
9 | 1st Floor - PASSAGE B | 1st Floor | 100% | 60% | 0% | 14.29% | 60% | 40% | 33.33% | 66.67% | 0% | 17 | 0 | 21 | 44.74% | IN PROGRESS | Mobilized | [5 empty] | 2nd Floor - PASSAGE B | 2nd Floor | 1 | 0.5 | 0 | 0.14286 | 0.6 | 0.4 | 0.33333 | 0.33333 | 0 | 15 | 0 | 23 | 0.39474 | 0 | IN PROGRESS | Mobilized | 1
10 | 1st Floor - PASSAGE C | 1st Floor | 100% | 60% | 0% | 14.29% | 60% | 40% | 33.33% | 50% | 0% | 16 | 1 | 21 | 43.42% | IN PROGRESS | Mobilized | [5 empty] | 2nd Floor - PASSAGE C | 2nd Floor | 1 | 0.5 | 0 | 0.14286 | 0.6 | 0.4 | 0.33333 | 0.33333 | 0 | 14 | 0 | 23 | 0.37838 | 0 | IN PROGRESS | Mobilized | 1
11 | 2nd Floor - PASSAGE A | 2nd Floor | 100% | 50% | 0% | 14.29% | 60% | 40% | 33.33% | 33.33% | 0% | 15 | 0 | 23 | 39.47% | IN PROGRESS | Mobilized | [5 empty] | 3rd Floor - PASSAGE A | 3rd Floor | 1 | 0.5 | 0 | 0.14286 | 0.6 | 0.4 | 0.33333 | 0.33333 | 0 | 15 | 0 | 23 | 0.39474 | 0 | IN PROGRESS | Mobilized | 1
12 | 2nd Floor - PASSAGE B | 2nd Floor | 100% | 50% | 0% | 14.29% | 60% | 40% | 33.33% | 33.33% | 0% | 15 | 0 | 23 | 39.47% | IN PROGRESS | Mobilized | [5 empty] | 3rd Floor - PASSAGE B | 3rd Floor | 1 | 0.5 | 0 | 0.14286 | 0.6 | 0.4 | 0.33333 | 0.33333 | 0 | 15 | 0 | 23 | 0.39474 | 0 | IN PROGRESS | Mobilized | 1
13 | 2nd Floor - PASSAGE C | 2nd Floor | 100% | 50% | 0% | 14.29% | 60% | 40% | 33.33% | 33.33% | 0% | 14 | 0 | 23 | 37.84% | IN PROGRESS | Mobilized | [5 empty] | 3rd Floor - PASSAGE C | 3rd Floor | 1 | 0.5 | 0 | 0.14286 | 0.6 | 0.4 | 0.33333 | 0.33333 | 0 | 15 | 0 | 23 | 0.39474 | 0 | IN PROGRESS | Mobilized | 1
14 | 3rd Floor - PASSAGE A | 3rd Floor | 100% | 50% | 0% | 14.29% | 60% | 40% | 33.33% | 33.33% | 0% | 15 | 0 | 23 | 39.47% | IN PROGRESS | Mobilized | [5 empty] | 4th Floor - PASSAGE A | 4th Floor | 1 | 0.4 | 0 | 0.14286 | 0.3 | 0.4 | 0.33333 | 0.16667 | 0 | 11 | 2 | 25 | 0.31579 | 0 | IN PROGRESS | Mobilized | 1
15 | 3rd Floor - PASSAGE B | 3rd Floor | 100% | 50% | 0% | 14.29% | 60% | 40% | 33.33% | 33.33% | 0% | 15 | 0 | 23 | 39.47% | IN PROGRESS | Mobilized | [5 empty] | 4th Floor - PASSAGE B | 4th Floor | 1 | 0.4 | 0 | 0.14286 | 0.3 | 0.4 | 0.33333 | 0.16667 | 0 | 11 | 2 | 25 | 0.31579 | 0 | IN PROGRESS | Mobilized | 1
16 | 3rd Floor - PASSAGE C | 3rd Floor | 100% | 50% | 0% | 14.29% | 60% | 40% | 33.33% | 33.33% | 0% | 15 | 0 | 23 | 39.47% | IN PROGRESS | Mobilized | [5 empty] | 4th Floor - PASSAGE C | 4th Floor | 1 | 0.4 | 0 | 0.14286 | 0.3 | 0.4 | 0.33333 | 0.16667 | 0 | 11 | 2 | 25 | 0.31579 | 0 | IN PROGRESS | Mobilized | 1
17 | 4th Floor - PASSAGE A | 4th Floor | 100% | 40% | 0% | 14.29% | 30% | 40% | 33.33% | 16.67% | 0% | 11 | 2 | 25 | 31.58% | IN PROGRESS | Mobilized | [5 empty] | Shear wall(lift) A | Service Areas / Stairs | 1 | 0 | 0 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 24 | 0.11111 | 0 | IN PROGRESS | Mobilized | 1
18 | 4th Floor - PASSAGE B | 4th Floor | 100% | 40% | 0% | 14.29% | 30% | 40% | 33.33% | 16.67% | 0% | 11 | 2 | 25 | 31.58% | IN PROGRESS | Mobilized | [5 empty] | Shear wall(lift) C | Service Areas / Stairs | 1 | 0 | 0 | 0.14286 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 24 | 0.11111 | 0 | IN PROGRESS | Mobilized | 1
19 | 4th Floor - PASSAGE C | 4th Floor | 100% | 40% | 0% | 14.29% | 30% | 40% | 33.33% | 16.67% | 0% | 11 | 2 | 25 | 31.58% | IN PROGRESS | Mobilized | [5 empty] | Stair case (STEP)A | Service Areas / Stairs | 1 | 0.0625 | 0 | 0.14286 | 0 | 0 | 0.5 | 0 | 0 | 3 | 2 | 23 | 0.14286 | 0 | IN PROGRESS | Mobilized | 1
20 | Shear wall(lift) A | Service Areas / Stairs | 100% | 0% | 0% | 14.29% | 0% | 0% | 0% | 0% | 0% | 3 | 0 | 24 | 11.11% | IN PROGRESS | Mobilized | [5 empty] | Stair case (STEP)B | Service Areas / Stairs | 1 | 0.0625 | 0 | 0.14286 | 0 | 0 | 0.5 | 0 | 0 | 3 | 2 | 23 | 0.14286 | 0 | IN PROGRESS | Mobilized | 1
21 | Shear wall(lift) C | Service Areas / Stairs | 100% | 0% | 0% | 14.29% | 0% | 0% | 0% | 0% | 0% | 3 | 0 | 24 | 11.11% | IN PROGRESS | Mobilized | [5 empty] | Stair case (STEP)C | Service Areas / Stairs | 1 | 0.0625 | 0 | 0.14286 | 0 | 0 | 0.5 | 0 | 0 | 3 | 2 | 23 | 0.14286 | 0 | IN PROGRESS | Mobilized | 1
22 | Stair case (STEP)A | Service Areas / Stairs | 100% | 6.25% | 0% | 14.29% | 0% | 0% | 50% | 0% | 0% | 3 | 2 | 23 | 14.29% | IN PROGRESS | Mobilized
23 | Stair case (STEP)B | Service Areas / Stairs | 100% | 6.25% | 0% | 14.29% | 0% | 0% | 50% | 0% | 0% | 3 | 2 | 23 | 14.29% | IN PROGRESS | Mobilized
24 | Stair case (STEP)C | Service Areas / Stairs | 100% | 6.25% | 0% | 14.29% | 0% | 0% | 50% | 0% | 0% | 3 | 2 | 23 | 14.29% | IN PROGRESS | Mobilized

## 100 ROOMS
ALL ROOMS WORK
Basic Details |  |  |  | Civil Work |  |  |  |  | WATERPROFFING |  |  | Electrical | [11 empty] | ELV |  | Plumbing | [8 empty] | Paint | [6 empty] | Fire |  |  |  | HVAC | [8 empty] | Tiles | [9 empty] | Furniture work | [10 empty] | Furnishing work | [5 empty] | Glass Work |  |  | Fixtures and OS&E
Room no | Floor | Room Type | Handover Target | Brickwork & Plaster Repairing | ROOM PLASTER | ROOM COBA | Bathroom Plaster | Bathroom COBA | BATHROOM CLEANING | BATHROOM WATERPROFFING | BATHROOM WATERPROFFING TESTING | Conduting | Wiring | FAN ROD | Cat-6 / WIFI Points | TV Points | Fire Alarm / Sounder cabling | Telephone / EPABX cabling | Switches work | light Fitting | DB BOX Installation | MCCB / RCCB installation | ROOM ELECTRICAL TESTING | Electronic Door Locks | ELV Funcitonal Testing | Core Cutting | Number of Core cutting | SWR | CPVC | Consealded / Internal fixture | Exposed / sanitary fixture | Final trap & Drain Connection | Final water flow / leakage Check | Pressure /Leakage Testing | Wall punning | 1st coat primer | 2 coat putty | 1 coat Primer | 1ST coat paint | 2ND coat paint | final touchup | Pipeline installatin work | sprinklers | Pipe line testing & painting | Smoke Detecters | Drain pipe | Copper piping | Condensed Drain Pipe | Copper piping | GI ducting / Fresh Air | VRV Indoor | VRV outdoors | Diffuser / Grille | HVAC Commissioning | Commercial tiles | Bathroom and Vestibule Floor tile | Bath room Wall tile | window framing | Black Italian patti | PANI PATTI | WALL EPOXY | framing work | board Fixing | final touchup | DOOR FRAME | Main door | Bathroom Door | Trap Door | Vanity Counter | Wardrobe+LUGGUAGE | Mini Bar | Bed Back Panelling | Pelmet | TV Unit | Loose Furniture | Rugs | Carpet | SPC Flooring | Curtain | Bed Back Cushioning | Art work / painting | Window Glass | Window Glass Silicon | Bathroom Glass partition | TV installation | Minibar fridge | Safe | kettle / Tea tray | Telephone | Bathroom accessories / hair dryer | Decorative lamps | Room accessories / signage
TOTAL |  |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
COMPLETED |  |  | 4061 | 13 | 56 | 32 | 100 | 29 | 100 | 100 | 100 | 100 | 99 | 98 | 99 | 98 | 0 | 0 | 2 | 2 | 98 | 2 | 2 | 2 | 0 | 100 | 0 | 100 | 100 | 99 | 2 | 0 | 0 | 100 | 100 | 92 | 90 | 91 | 2 | 0 | 2 | 100 | 92 | 82 | 2 | 100 | 100 | 100 | 82 | 82 | 99 | 0 | 0 | 0 | 99 | 99 | 94 | 97 | 99 | 96 | 2 | 68 | 50 | 2 | 93 | 29 | 7 | 40 | 3 | 2 | 2 | 2 | 95 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 2 | 73 | 86 | 56 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 0
NOT STARTED |  |  | 4080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 2 | 100 | 100 | 98 | 52 | 2 | 98 | 98 | 97 | 100 | 0 | 0 | 0 | 0 | 1 | 97 | 99 | 99 | 0 | 0 | 4 | 7 | 9 | 98 | 100 | 98 | 0 | 8 | 18 | 98 | 0 | 0 | 0 | 18 | 18 | 1 | 100 | 100 | 100 | 0 | 1 | 4 | 3 | 1 | 4 | 98 | 2 | 2 | 7 | 6 | 12 | 44 | 59 | 97 | 96 | 96 | 96 | 5 | 67 | 96 | 98 | 98 | 98 | 98 | 100 | 98 | 18 | 11 | 43 | 98 | 100 | 100 | 100 | 100 | 100 | 98 | 100
ON GOING |  |  | 476 | 87 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 0 | 30 | 48 | 91 | 1 | 59 | 49 | 1 | 0 | 2 | 2 | 2 | 0 | 31 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NOT VALID |  |  | 183 | 0 | 44 | 68 | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
101 | 1st floor | King room |  | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | COMPLETED | COMPLETED | ON GOING | COMPLETED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
102 | 1st floor | King room |  | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED
103 | 1st floor | Twin room |  | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED
104 | 1st floor | Twin room |  | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
105 | 1st floor | King room |  | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | COMPLETED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
106 | 1st floor | King room |  | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | COMPLETED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
107 | 1st floor | Twin room |  | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | COMPLETED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
108 | 1st floor | Twin room |  | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | ON GOING | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
109 | 1st floor | King room |  | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | COMPLETED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
110 | 1st floor | Twin room |  | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | COMPLETED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
111 | 1st floor | King room |  | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | COMPLETED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
112 | 1st floor | Twin room |  | COMPLETED | COMPLETED | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
113 | 1st floor | King room |  | COMPLETED | COMPLETED | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | COMPLETED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
114 | 1st floor | King room |  | ON GOING | COMPLETED | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
115 | 1st floor | Twin room |  | ON GOING | COMPLETED | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
116 | 1st floor | King room |  | ON GOING | COMPLETED | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
117 | 1st floor | Twin room |  | ON GOING | COMPLETED | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
118 | 1st floor | Suite room |  | ON GOING | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
119 | 1st floor | Twin room |  | ON GOING | NOT VALID | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
120 | 1st floor | King room |  | ON GOING | NOT VALID | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
121 | 1st floor | Suite room |  | ON GOING | NOT VALID | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 10 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | NOT STARTED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
122 | 1st floor | Suite room |  | ON GOING | COMPLETED | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 6 | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
123 | 1st floor | King room |  | ON GOING | NOT VALID | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | COMPLETED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
124 | 1st floor | King room |  | ON GOING | COMPLETED | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | ON GOING | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | COMPLETED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
201 | 2nd floor | King room |  | ON GOING | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | COMPLETED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
202 | 2nd floor | King room |  | ON GOING | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | COMPLETED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
203 | 2nd floor | Twin room |  | ON GOING | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | COMPLETED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
204 | 2nd floor | Twin room |  | ON GOING | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | COMPLETED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
205 | 2nd floor | King room |  | ON GOING | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | COMPLETED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
206 | 2nd floor | King room |  | ON GOING | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | ON GOING | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
207 | 2nd floor | Twin room |  | ON GOING | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | COMPLETED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
208 | 2nd floor | Twin room |  | ON GOING | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | COMPLETED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
209 | 2nd floor | King room |  | ON GOING | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
210 | 2nd floor | Twin room |  | ON GOING | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
211 | 2nd floor | King room |  | ON GOING | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | ON GOING | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
212 | 2nd floor | Twin room |  | ON GOING | COMPLETED | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
213 | 2nd floor | King room |  | ON GOING | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | COMPLETED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
214 | 2nd floor | King room |  | ON GOING | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | ON GOING | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
215 | 2nd floor | Twin room |  | ON GOING | COMPLETED | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | ON GOING | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
216 | 2nd floor | King room |  | ON GOING | NOT VALID | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
217 | 2nd floor | Twin room |  | ON GOING | NOT VALID | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | COMPLETED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
218 | 2nd floor | King room |  | ON GOING | NOT VALID | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
219 | 2nd floor | King room |  | ON GOING | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | ON GOING | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
220 | 2nd floor | King room |  | ON GOING | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | ON GOING | ON GOING | COMPLETED | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
221 | 2nd floor | King room |  | ON GOING | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | ON GOING | ON GOING | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
222 | 2nd floor | Twin room |  | ON GOING | NOT VALID | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | ON GOING | ON GOING | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
223 | 2nd floor | King room |  | ON GOING | COMPLETED | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
224 | 2nd floor | Suite room |  | ON GOING | NOT VALID | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 10 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
225 | 2nd floor | Suite room |  | ON GOING | NOT VALID | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 7 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
226 | 2nd floor | King room |  | ON GOING | NOT VALID | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
227 | 2nd floor | King room |  | ON GOING | COMPLETED | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | ON GOING | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
228 | 2nd floor | King room |  | ON GOING | COMPLETED | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | ON GOING | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
229 | 2nd floor | King room |  | ON GOING | COMPLETED | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | ON GOING | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
230 | 2nd floor | King room |  | ON GOING | COMPLETED | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | ON GOING | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
301 | 3rd floor | King room |  | ON GOING | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
302 | 3rd floor | King room |  | ON GOING | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
303 | 3rd floor | Twin room |  | ON GOING | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
304 | 3rd floor | Twin room |  | ON GOING | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
305 | 3rd floor | King room |  | ON GOING | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | ON GOING | ON GOING | COMPLETED | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
306 | 3rd floor | King room |  | ON GOING | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | ON GOING | ON GOING | COMPLETED | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
307 | 3rd floor | Twin room |  | ON GOING | COMPLETED | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | ON GOING | ON GOING | COMPLETED | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
308 | 3rd floor | Twin room |  | ON GOING | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | ON GOING | ON GOING | COMPLETED | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
309 | 3rd floor | King room |  | ON GOING | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
310 | 3rd floor | Twin room |  | ON GOING | COMPLETED | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | ON GOING | ON GOING | COMPLETED | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
311 | 3rd floor | King room |  | ON GOING | COMPLETED | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | ON GOING | ON GOING | COMPLETED | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
312 | 3rd floor | Twin room |  | ON GOING | COMPLETED | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | ON GOING | ON GOING | COMPLETED | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
313 | 3rd floor | King room |  | ON GOING | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
314 | 3rd floor | King room |  | ON GOING | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 6 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
315 | 3rd floor | Twin room |  | ON GOING | NOT VALID | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
316 | 3rd floor | King room |  | ON GOING | NOT VALID | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
317 | 3rd floor | Twin room |  | ON GOING | NOT VALID | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
318 | 3rd floor | King room |  | ON GOING | NOT VALID | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
319 | 3rd floor | King room |  | ON GOING | NOT VALID | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
320 | 3rd floor | Twin room |  | ON GOING | COMPLETED | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
321 | 3rd floor | King room |  | ON GOING | COMPLETED | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
322 | 3rd floor | King room |  | ON GOING | COMPLETED | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
323 | 3rd floor | Suite room |  | ON GOING | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 6 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
324 | 3rd floor | King room |  | ON GOING | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
325 | 3rd floor | King room |  | ON GOING | NOT VALID | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
326 | 3rd floor | King room |  | ON GOING | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
327 | 3rd floor | King room |  | ON GOING | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
328 | 3rd floor | King room |  | ON GOING | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | ON GOING | ON GOING | COMPLETED | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
401 | 4th floor | King room |  | ON GOING | COMPLETED | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
402 | 4th floor | Twin room |  | ON GOING | COMPLETED | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
403 | 4th floor | King room |  | ON GOING | COMPLETED | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
404 | 4th floor | Twin room |  | ON GOING | COMPLETED | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
405 | 4th floor | King room |  | ON GOING | COMPLETED | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
406 | 4th floor | King room |  | ON GOING | COMPLETED | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
407 | 4th floor | Twin room |  | ON GOING | COMPLETED | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
408 | 4th floor | King room |  | ON GOING | NOT VALID | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
409 | 4th floor | Twin room |  | ON GOING | NOT VALID | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
410 | 4th floor | King room |  | ON GOING | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
411 | 4th floor | King room |  | ON GOING | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
412 | 4th floor | King room |  | ON GOING | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
413 | 4th floor | Suite room |  | ON GOING | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 7 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | ON GOING | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
414 | 4th floor | King room |  | ON GOING | COMPLETED | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
415 | 4th floor | King room |  | ON GOING | NOT VALID | COMPLETED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
416 | 4th floor | King room |  | ON GOING | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
417 | 4th floor | King room |  | ON GOING | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | ON GOING | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
418 | 4th floor | King room |  | ON GOING | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | 5 | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | ON GOING | ON GOING | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
Total Rooms | 100 rooms
RESTAURANT | Ground Floor
KITCHEN
BOH Area
Banquet 2
Reception
Wedding Boutique
Confrance hall
Reception Toilets
Private Cabins
Banquet 3
Banquete Hall
PreFunction Area
Banquete Kitchen
Common toilet
Electrical Room | First Floor
BOH Area
Waiting Area
Panal Room
Electrical Room | Second Floor
BOH Room
Waiting Area
Panal Room
Terrace
Electrical Room | Third Floor
BOH Room
Waiting Area
Panal Room
Electrical Room | fourth Floor
BOH Room
Waiting Area
Panal Room
Swimming pool BOH
Swimming pool | Terrace
Deck
Gym
Changing Room
Survice Room
Terrace For Service
OH water tank
OH fire tank
plumbing vertical line
connection OHT to UGT
STP work Equpment
Connection OHT to UGT
Earthing & testing

## PUBLIC AREA
PUBLIC AREA
S. No. | AREA |  | Civil Work | [43 empty] | Tiles | [7 empty] | Furniture Work |  |  |  | Furnishing and Decor |  |  |  | GLASS
|  |  | Brickwork | Plaster | Repairing Work | Conduting | Light Wire | Switches Work | Light Fixing | Main DB / MCB Installation | Speaker Wire | CAT-6 | CCTV Wire | Wi-Fi Cable | EPABX + Wi-Fi + CCTV | Music / PA System | Core Cutting | Horizontal SWR | Horizontal CPVC | Plumbing Testing | Internal Fixture | External Fixture | Final Testing | White Cement / primer | Wall Punning | Putty1 | Putty2 | Primer | Paint 1 | Paint 2 | Final Paint Touchup | Fire Alarm Cable | Fire Alarm System | Pipeline Installatin Work | Sprinklers | Pipeline Testing | Speakers / Sounder | Smoke Detecters | Final Testing | Copper piping + Drain pipe | GI Ducting | Diffuser & Grille Frames | Exhaust & Fresh Air Lines | AHU / Indoors Placement | AHU / Outdoors Placement | Final Testing | Floor tiles | Wall tiles | Skirting | Window / Door Granite | Floor Granite | Framing Work | Board Fixing | Final Touchup | Aluminium Work | Ply Work | Final Mica Work | Loose Furniture | Carpet / Rug | Curtains | Artwork | Internal Signages | WINDOW
1 | All Day Dining Area | GROUND FLOOR | ON GOING | ON GOING |  | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
2 | Receiption Area |  | ON GOING | ON GOING |  | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT VALID | NOT STARTED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT VALID
3 | Banquet 2 |  | COMPLETED | NOT VALID |  | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT VALID | NOT VALID | NOT STARTED | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | COMPLETED | ON GOING | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT VALID
| Banquet 2 Pre Function |  | COMPLETED | COMPLETED |  | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
4 | Wedding Boutique |  | COMPLETED | COMPLETED |  | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | COMPLETED | NOT VALID | COMPLETED | NOT VALID | NOT VALID | NOT STARTED | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
5 | Banquet 3 |  | COMPLETED | COMPLETED |  | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | COMPLETED | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | COMPLETED | ON GOING | NOT STARTED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
| Banquet 3 Pre Function |  | NOT STARTED | NOT STARTED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
6 | Conference Room |  | COMPLETED | COMPLETED |  | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT VALID | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
7 | Owners Cabin |  | COMPLETED | COMPLETED |  | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
8 | G M Office |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
9 | Utility Store |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
10 | Male Toilet |  | COMPLETED | COMPLETED |  | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | NOT STARTED | NOT VALID | NOT STARTED | ON GOING | ON GOING | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID
11 | Female Toilet |  | COMPLETED | COMPLETED |  | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | NOT STARTED | NOT VALID | NOT STARTED | ON GOING | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID
12 | BACK OFFICE |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
| Luggage Room |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
13 | Complete Passage Area |  | COMPLETED | COMPLETED |  | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | COMPLETED | NOT VALID | COMPLETED | NOT VALID | NOT VALID | NOT STARTED | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
14 | Live Kitchen |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT VALID | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
15 | Dish Wash Area |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT VALID | NOT VALID | NOT STARTED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
16 | Back Kitchen |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT VALID | NOT VALID | NOT STARTED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
17 | Pot Wash |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT VALID | NOT VALID | NOT STARTED | COMPLETED | NOT VALID | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
18 | Veg Prep Area |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT VALID | NOT VALID | NOT STARTED | COMPLETED | NOT VALID | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT VALID | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
19 | Walk-In Refridgerator |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT VALID | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
20 | Main Store |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT VALID | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
21 | IT Server Room |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT VALID | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
22 | Beverage Store |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT VALID | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
23 | HR Manager |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
| Open Office |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
| Record Room |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
| Account Manager |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
24 | Meeting Room |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | NOT VALID | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
25 | Bakery |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
| Walkin Refridgerator |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | COMPLETED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
26 | Room Service |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
27 | Cafetaria |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT VALID | NOT VALID | NOT STARTED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
| Staff Dish Wash |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT VALID | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
28 | Laundry Area |  | ON GOING | ON GOING |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | ON GOING | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
29 | Electrical Panel Room |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
| Chief Engg. Manger |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
| Engineerng Store |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
30 | Garbage Area |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
31 | Receving Area |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
32 | CCTV Room |  | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT VALID | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
33 | Security office |  | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT VALID | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
34 | Service Left Area |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
35 | Banquet 1 Area |  | COMPLETED | ON GOING |  | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT VALID | NOT STARTED | NOT VALID | NOT STARTED | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
| Banquet Spill Out |  | COMPLETED | ON GOING |  | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | NOT VALID | NOT STARTED | NOT VALID | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
| Pre Function |  | NOT STARTED | NOT STARTED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
| Passage Entry |  | COMPLETED | ON GOING |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
| Male Toilet |  | COMPLETED | ON GOING |  | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
| Female Toilet |  | COMPLETED | ON GOING |  | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
| Banquet Furniture Store |  | ON GOING | ON GOING |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT VALID | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
| Banquet Dish wash |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
| main Kitchen |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT VALID | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT STARTED | ON GOING | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
36 | Swimming pool Area | TERRACE | ON GOING | ON GOING |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT VALID | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
| Deck Area |  | ON GOING | NOT STARTED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
| Gym |  | ON GOING | NOT STARTED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
| Male Changing Room |  | ON GOING | NOT STARTED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
| Female Chaning Room |  | ON GOING | NOT STARTED |  | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
37 | RAIN DANCE |  | ON GOING | NOT VALID |  | NOT VALID | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT VALID | NOT STARTED | NOT VALID | NOT VALID | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT STARTED | NOT VALID | NOT VALID | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID
38 | WAITING AREA(B) | 1st FLOOR | COMPLETED | COMPLETED |  | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
| WAITING AREA(C) |  | COMPLETED | COMPLETED |  | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED
| ELEctrical Panel Room |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID
39 | WAITING AREA(B) | 2nd FLOOR | COMPLETED | COMPLETED |  | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
| WAITING AREA(C) |  | COMPLETED | COMPLETED |  | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED
| ELEctrical Panel Room |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID
40 | WAITING AREA(B) | 3rd FLOOR | COMPLETED | COMPLETED |  | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
| WAITING AREA(C) |  | COMPLETED | COMPLETED |  | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED
| ELEctrical Panel Room |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID
41 | WAITING AREA(B) | 4th FLOOR | COMPLETED | COMPLETED |  | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
| WAITING AREA(C) |  | COMPLETED | COMPLETED |  | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT VALID | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED
| ELEctrical Panel Room |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT VALID | NOT VALID | NOT VALID | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID
| SERVICE AREA |  | COMPLETED | COMPLETED |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT STARTED | NOT VALID | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID

## PASSAGE
AREA | FLOOR | Civil Work |  | ELECTRICAL | [9 empty] | PLUMBING |  | Paint | [6 empty] | Fire |  |  |  |  | HVAC |  |  |  |  | Tiles |  |  |  |  | False Ceiling |  |  | Testing
|  | Brickwork | Plaster | Conduting | CABLE TRAY | CAT-6 | SPEAKER WIRE | ALARM WIRE | ARMT CABLE | EPABX + WIFI + CCTV | switches work | light fixing | Main DB / MCB installation | HORIGENTLE SWR | HORIGENTLE CPVC | Wall punning | BIRLA WHITE | putty | Primer | paint | final touchup | texture | Pipeline installatin work | sprinklers | pipeline testing | Speakers | Smoke Detecters | Copper piping + Drain pipe | GI ducting | Diffuser & grille frames | Exhaust & fresh air lines | AHU placement | GRANITE | Kota stone | Commercial tiles | SPC FLOORING | CARPET WORK | framing work | board Fixing | final touchup | Electrical load testing | Fire alarm cause & effect testing | HVAC balancing test
GROUND FLOOR | LOUNDRY AREA PASSAGE | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED |  |  |  |  | NOT VALIDE | NOT VALIDE
| CAFETERIA PASSAGE | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED |  |  |  |  | NOT VALIDE | NOT VALIDE
| BANQUATE-1 PASAGE | ON GOING | ON GOING | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
| MAIN KITCHEN PASAGE | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
| BANQUATE 3 PASSAGE | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
| RECEPTION PASSAGE | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
| CABINE PASSAGE | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
1st FLOOR | PASSAGE A | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALIDE | NOT VALIDE | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALIDE | NOT VALIDE | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
| PASSAGE B | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALIDE | NOT VALIDE | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALIDE | NOT VALIDE | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
| PASSAGE C | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALIDE | NOT VALIDE | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALIDE | NOT VALIDE | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
2nd FLOOR | PASSAGE A | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALIDE | NOT VALIDE | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALIDE | NOT VALIDE | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
| PASSAGE B | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALIDE | NOT VALIDE | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALIDE | NOT VALIDE | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
| PASSAGE C | COMPLETED | NOT VALIDE | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALIDE | NOT VALIDE | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALIDE | NOT VALIDE | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
3rd FLOOR | PASSAGE A | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALIDE | NOT VALIDE | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALIDE | NOT VALIDE | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
| PASSAGE B | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALIDE | NOT VALIDE | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALIDE | NOT VALIDE | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
| PASSAGE C | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALIDE | NOT VALIDE | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALIDE | NOT VALIDE | COMPLETED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
4th FLOOR | PASSAGE A | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALIDE | NOT VALIDE | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | ON GOING | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALIDE | NOT VALIDE | COMPLETED | NOT STARTED | NOT STARTED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
| PASSAGE B | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALIDE | NOT VALIDE | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | ON GOING | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALIDE | NOT VALIDE | COMPLETED | NOT STARTED | NOT STARTED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
| PASSAGE C | COMPLETED | COMPLETED | NOT STARTED | COMPLETED | NOT STARTED | COMPLETED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALIDE | NOT VALIDE | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | COMPLETED | NOT STARTED | ON GOING | NOT STARTED | NOT STARTED | COMPLETED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALIDE | NOT VALIDE | COMPLETED | NOT STARTED | NOT STARTED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED
Shear wall(lift) A |  | COMPLETED | COMPLETED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED |  |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALIDE | NOT VALIDE | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID
Shear wall(lift) C |  | COMPLETED | COMPLETED | NOT STARTED | NOT VALID | NOT STARTED | NOT STARTED |  |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALIDE | NOT VALIDE | NOT STARTED | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID
Stair case (STEP)A |  | COMPLETED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED |  |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALIDE | NOT VALIDE | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID
Stair case (STEP)B |  | COMPLETED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED |  |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALIDE | NOT VALIDE | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID
Stair case (STEP)C |  | COMPLETED | COMPLETED | ON GOING | NOT STARTED | NOT STARTED | NOT STARTED |  |  | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT VALIDE | NOT VALIDE | COMPLETED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | NOT STARTED | ON GOING | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID | NOT VALID